## Cover
THE
DECISION-GRADE PMO
COMPANION PACK
Editable tools for turning AI-assisted PMO work into defensible decisions.
START WITH THE WORKBOOK MAP
Open the Index tab, choose the decision or operating problem you are working on, then adapt the relevant template—not the governance discipline behind it.
5 MASTER TEMPLATES | 21 CHAPTER TOOLKITS
75 GOVERNED PROMPTS · QUICK-REFERENCE GLOSSARY · CHANGE LOG
STEVEN A THOMSON
© 2026 Steven A Thomson · All rights reserved · Templates may be adapted and used inside your organisation

## Index
Workbook map
The Decision-Grade PMO · Companion Pack
5 MASTER TEMPLATES |  | 21 CHAPTER TOOLKITS | 75 GOVERNED PROMPTS | 1 WORKING SYSTEM
# | RESOURCE | TAB | PURPOSE
HOW TO USE
01 | How to use this pack | How_to_Use | Adaptation guidance, the starting-point principle, and copyright/usage notes.
MASTER TEMPLATES
02 | Master Templates M1–M5 | Master_Templates | The five templates used across every domain service.
PER-CHAPTER TEMPLATES
03 | Chapter 1 — The PMO Reality Check | Ch01_The_PMO_Reality_Check | Templates and checklists from Chapter 1 of the book. 5 templates; 2 checklists.
04 | Chapter 2 — From Tools to Nerve Centre Thinking | Ch02_From_Tools_to_Nerve_Cent | Templates and checklists from Chapter 2 of the book. 7 templates; 3 checklists.
05 | Chapter 3 — What AI Can and Cannot Do in a PMO | Ch03_What_AI_Can_and_Cannot_D | Templates and checklists from Chapter 3 of the book. 6 templates; 3 checklists.
06 | Chapter 4 — Governance, Accountability, and Human-in-the-Loop | Ch04_Governance_Accountabilit | Templates and checklists from Chapter 4 of the book. 8 templates; 3 checklists.
07 | Chapter 5 — Data Readiness and Evidence Standards | Ch05_Data_Readiness_and_Evide | Templates and checklists from Chapter 5 of the book. 7 templates; 2 checklists.
08 | Chapter 6 — Designing the PMO Operating Process for AI | Ch06_Designing_the_PMO_Operat | Templates and checklists from Chapter 6 of the book. 7 templates; 3 checklists.
09 | Chapter 7 — AI in Integrated Planning and Scheduling | Ch07_AI_in_Integrated_Plannin | Templates and checklists from Chapter 7 of the book. 7 templates; 3 checklists.
10 | Chapter 8 — AI in Cost and Estimating | Ch08_AI_in_Cost_and_Estimatin | Templates and checklists from Chapter 8 of the book. 9 templates; 3 checklists.
11 | Chapter 9 — AI in Risk Management and Quantitative Risk Analysis | Ch09_AI_in_Risk_Management_an | Templates and checklists from Chapter 9 of the book. 8 templates; 3 checklists.
12 | Chapter 10 — AI in Change and Contract Management | Ch10_AI_in_Change_and_Contrac | Templates and checklists from Chapter 10 of the book. 8 templates; 3 checklists.
13 | Chapter 11 — AI in Resource and Capability Management | Ch11_AI_in_Resource_and_Capab | Templates and checklists from Chapter 11 of the book. 10 templates; 4 checklists.
14 | Chapter 12 — AI in Reporting, Performance, and Insight | Ch12_AI_in_Reporting_Performa | Templates and checklists from Chapter 12 of the book. 8 templates; 4 checklists.
15 | Chapter 13 — Digital & Data Architecture for the Digital PMO | Ch13_Digital_Data_Architectur | Templates and checklists from Chapter 13 of the book. 7 templates; 3 checklists.
16 | Chapter 14 — Assurance, Compliance, and Audit in an AI Context | Ch14_Assurance_Compliance_and | Templates and checklists from Chapter 14 of the book. 8 templates; 3 checklists.
17 | Chapter 15 — Stakeholders, Communication, and Trust | Ch15_Stakeholders_Communicati | Templates and checklists from Chapter 15 of the book. 7 templates; 4 checklists.
18 | Chapter 16 — The Predictive PMO in Operation | Ch16_The_Predictive_PMO_in_Op | Templates and checklists from Chapter 16.
19 | Chapter 17 — Building the Digital PMO Roadmap | Ch17_Building_the_Digital_PMO | Templates and checklists from Chapter 17 of the book. 6 templates; 4 checklists.
20 | Chapter 18 — Operating Model, Roles, and Capability Uplift | Ch18_Operating_Model_Roles_an | Templates and checklists from Chapter 18 of the book. 8 templates; 3 checklists.
21 | Chapter 19 — Failure Modes, Ethics, and Risk Management | Ch19_Failure_Modes_Ethics_and | Templates and checklists from Chapter 19 of the book. 6 templates; 4 checklists.
22 | Chapter 20 — Measuring Value Without Chasing Vanity Metrics | Ch20_Measuring_Value_Without | Templates and checklists from Chapter 20 of the book. 6 templates; 3 checklists.
23 | Chapter 21 — The PMO as Decision Advantage | Ch21_The_PMO_as_Decision_Adva | Templates and checklists from Chapter 21 of the book. 5 templates; 3 checklists.
PROMPT PACK
24 | Prompt Pack (all 75) | Prompts_All | Every prompt from Appendix D. Use the filter on the Workflow column to view by stage, or the Chapter column to cross-reference.
REFERENCE
25 | Glossary | Glossary | Quick-reference acronyms and key terms used across the templates.
26 | Change log | Change_Log | What has changed in this pack, and when.
THE DECISION-GRADE PMO · COMPANION PACK · Index

## How_to_Use
How to use this pack
A working companion to the book—not a substitute for its operating discipline
01 START WITH THE DECISION Name the decision, its owner, option window and evidence need before selecting a tool. |  | 02 ADAPT THE FORM Change labels and fields to fit your context. Preserve the accountability, evidence and publication controls. | 03 LEAVE A RECORD Version the output, record evidence and approval, and make the decision trail retrievable.
THE PRINCIPLE THIS PACK RESTS ON
DISCIPLINE FIRST, TEMPLATES SECOND.
The book is about an operating discipline — Publication Gate, Evidence Spine, Level of Autonomy, decision services. The templates in this pack are one way to operate that discipline. They are not the discipline itself. A PMO that runs the discipline without these templates is closer to decision-grade than a PMO that follows these templates without the discipline.
ADAPT, DON'T FOLLOW.
Every template carries [modify for context] markers at the points where local adaptation is expected. Field names, sections, and even whole templates can be added, removed, renamed, or replaced. The right test is not 'have I filled in all the fields' but 'does this output give my forum what it needs to decide?'
USE WHAT YOU NEED; IGNORE THE REST.
Most readers will use perhaps a third of this pack. That is the intended outcome. Pick the templates that solve a problem you have today. Leave the others in the pack for when you need them. There is no completion ladder.
TEMPLATES CAN BE REPLACED WHOLESALE.
If your organisation has a better template — from your existing operating model, from your assurance partner, from a previous programme — use that. The Master Failure Mode Taxonomy, the LoA ladder, and the Three Numbers discipline are the load-bearing concepts; the specific template forms here are interchangeable.
HOW TO NAVIGATE THIS PACK
WORKBOOK ROUTE · A PRACTICAL FIRST PASS
□ | Start at the Index sheet for the full list of sheets and tab names.
□ | Read Master_Templates first — the four cross-service templates (M1–M4) are referenced from every chapter.
□ | For your first NC service, open the chapter sheet for that domain (e.g. Ch07_Planning for a planning service).
□ | Open Prompts_All to find the prompt pack — filter by Workflow column to see Diagnose / Frame / Build / Triage / Publish / Assure / Measure.
□ | Use Glossary if a term is unfamiliar.
COPYRIGHT AND USAGE
These templates may be adapted and used inside your organisation, on programmes you work on, and in client engagements you deliver. Attribution to The Decision-Grade PMO is appreciated but not required for internal use. Do not redistribute the pack itself — point colleagues to where they can obtain it. Contact the author for commercial reuse, derivative training products, or large-scale incorporation into commercial offerings.
THE DECISION-GRADE PMO · COMPANION PACK · How_to_Use

## Master_Templates
Master Templates M1–M5
The Decision-Grade PMO · Companion Pack
M1–M5 are the templates the rest of the book references. Most chapters use them as-is; chapter-specific templates extend or vary them. Adapt the field set to your context. M1–M4 are the minimum practical starting point; add M5 when the first AI-assisted step in a service goes live.
5 MASTER TEMPLATES · USE ACROSS ALL DOMAIN SERVICES |  |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
M1 | Master Template M1 — Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decisions this service supports
Service owner (accountable, named role)
Decision owner (forum + role)
Cadence (weekly / monthly / stage-gate)
Inputs (KDEs and systems-of-record)
Validations (KDE thresholds, reasonableness)
Outputs (publishable artefacts)
Gates (review / approve / publish)
LoA by output (0 None / 1 Assist / 2 Recommend / 3 Route / 4 Publish-restricted)
Evidence standard
Confidentiality classification and audience variants
Known failure modes (link to FM-X1–FM-X6)
Safe mode triggers
M2 | Master Template M2 — Publication Gate Checklist
Single gate instrument used across all six domain services and every governance-facing output. Walk this checklist before any output is released to a governance forum, audit, regulator, or external party.
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | KDE lineage complete: every numeric claim traceable to a named KDE with refresh date within the policy window
□ | Evidence at cut-off: the Evidence Spine entries for this output exist and are stored
□ | LoA declared and appropriate: the autonomy posture is named and matches the consequence class of the output
□ | Named human sign-off: a specific person (not a role inbox) is recorded as reviewer and approver, with date
□ | Traceability to source: a sample of three claims can be walked back to source data within ten minutes
□ | Contestability route: stakeholders know how to challenge the output (and a recent challenge response is on file)
□ | Limitations block present: where evidence is weak, the limitation is declared in the output itself
□ | Audience variant correct: the right version is going to the right audience; cleared / restricted content is segregated
□ | Distribution log updated: who received what version, when, recorded
□ | Prompt and template versions referenced: where AI-assisted, the prompt/template version IDs are stored with the output
M3 | Master Template M3 — Evidence Index
Claim ID |  | Claim text (one line) |  | Source system | Cut-off timestamp | Transformation path | Steward (named) | LoA
M4 | Master Template M4 — Role RACI
Activity |  | Service Owner |  | Data Steward | AI Assurance | Publication Gate Signatory | Sponsor | Notes
Define KDE catalogue
Set LoA by output
Sign Publication Gate
Approve safe-mode trigger
Distribute audience variant
Resolve evidence challenge
Authorise prompt change
Authorise model change
M5 | Master Template M5 — AI Quality Plan
Dimension |  |  |  |  | What the plan must answer, and where the evidence comes from
Product quality: is the capability any good?
Accuracy |  |  |  |  | How well does it do the task, measured how, and against what? Evidence: the validation record (Chapter 16, Table 16.2).
Robustness |  |  |  |  | How does it behave on inputs it was not built for? Evidence: sensitivity and scenario testing.
Reliability |  |  |  |  | Same answer from the same inputs, and available when the cycle needs it? Evidence: reproducibility test at the Gate; availability record.
Explainability |  |  |  |  | Can a reviewer see why the output says what it says, in terms they can argue with? Evidence: reviewer walkthrough; the Evidence Index.
Reproducibility |  |  |  |  | Can the output be regenerated from the same snapshots at the same cut-off? Evidence: the Chapter 5 evidence standard.
Security |  |  |  |  | Who can reach the data, the prompts, the logs and the outputs? Evidence: access control tests (Chapter 13).
Privacy |  |  |  |  | What personal or people data does it touch, and on what basis? Evidence: the privacy assessment (Chapter 19).
Data dependency |  |  |  |  | Which KDEs must be healthy for this to work, and what happens when one is not? Evidence: the KDE quality matrix (Table 5.1).
Resilience to missing or abnormal data |  |  |  |  | What does it do when an input is absent, late or implausible? Does it say so, or does it fill the gap? Evidence: negative testing; the safe-mode trigger list.
Quality in use: is it any good for the people who rely on it?
Decision usefulness |  |  |  |  | Does the output change what the forum can decide, or only what it can read? Evidence: value hypothesis and scorecard (Chapter 20).
User comprehension |  |  |  |  | Do the people who must act on it read it the way it was meant? Evidence: review of misreadings; audience-variant testing (Ch 15).
Controllability |  |  |  |  | Can a user stop it, narrow it, or run it differently? Evidence: the safe-mode trigger list (Chapter 4).
Operational reliability |  |  |  |  | Does it hold up across a full governance cycle, under real load and real deadlines? Evidence: cycle-level service measures.
Accessibility |  |  |  |  | Can it be used by people with different access needs and different levels of technical fluency? Evidence: accessibility check on output formats.
Consequences of error |  |  |  |  | Worst credible outcome of a wrong output reaching a decision, and who carries it? Evidence: consequence classification (Ch 19).
Ability to challenge or override |  |  |  |  | Can a user disagree, and does disagreement leave a record? Evidence: override log; contestability route.
Fitness for the governance purpose |  |  |  |  | Is this the right instrument for the decision it is being used in? Evidence: the LoA declaration and the Publication Gate.
THE DECISION-GRADE PMO · COMPANION PACK · Master_Templates

## Ch01_The_PMO_Reality_Check
Chapter 1 — The PMO Reality Check
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 5 TEMPLATES · 2 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
1.1 | Template 1.1 — Decision and Option Window Map
Decision |  | Forum |  | Decision owner | When options start narrowing | When options close | Evidence required | Primary outputs
1.2 | Template 1.2 — Decision Friction Log
FIELD / CONTROL |  |  | WORKING ENTRY
Friction point
Where it occurs
Symptom
Root cause hypothesis
Impact on decisions
Owner
Fix
Due
1.3 | Template 1.3 — Forum Decision Pack Standard
FIELD / CONTROL |  |  | WORKING ENTRY
Forum name and cadence
Decision types covered
Materiality thresholds
Pack spine (facts → exceptions → options → decisions/actions)
Required fields and definitions
Cut-off and freeze window
Reviewer and approver roles
Confidentiality variants and distribution
1.4 | Template 1.4 — Publication Record (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Pack/output name
Period and cut-off
Version ID
Source references (systems-of-record)
Prepared by / reviewed by / approved by (date/time)
Distribution (audience variant + recipients)
Limitations declared
1.5 | Template 1.5 — First-Wave Service Selection
FIELD / CONTROL |  |  | WORKING ENTRY
Candidate service
Decisions supported
Frequency
Consequence
Data controllability
Confidentiality risk
Why first
Owner
1A | Checklist 1A — PMO reality check (30–60 minute diagnostic)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | We can list our top recurring governance decisions
□ | We know when option windows close for each decision
□ | We can state what “decision-grade” means per forum
□ | Our packs end with decisions/actions (not commentary)
□ | Cut-offs are explicit and enforced
□ | Approvals are recorded for governance-facing outputs
□ | We can retrieve supporting evidence without document hunts
□ | Sensitive content uses controlled variants and distribution logs
1B | Checklist 1B — AI readiness (minimum viable)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Accountability and decision rights are explicit
□ | Definitions are stable enough to compare across projects
□ | Evidence handling is adequate for challenge and audit
□ | We can run one Thin-Slice service end-to-end with gates
THE DECISION-GRADE PMO · COMPANION PACK · Ch01_The_PMO_Reality_Check

## Ch02_From_Tools_to_Nerve_Cent
Chapter 2 — From Tools to Nerve Centre Thinking
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 7 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
2.1 | Template 2.1 — Decision Set and Owners List
Decision |  | Forum |  | Decision owner | Frequency | Option window (when choices narrow/close) | Evidence required | Notes
2.2 | Template 2.2 — Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision supported
Cadence (weekly/monthly/stage-gate)
Users (forum and audience variants)
Inputs (systems-of-record and controlled documents)
Validations (quality/reasonableness)
Outputs (exceptions/options/packs/logs)
Gates (review/approve/publish)
Evidence bundle requirements
Confidentiality classification and distribution
Owner(s)
Known limitations
2.3 | Template 2.3 — Service-to-Domain Integration Map
Service |  | Capability domains contributing |  | Key join identifiers |  | Definition owners | Escalation route for conflicts | Notes
2.4 | Template 2.4 — NC Cadence Map (fast triage + formal governance)
Cycle |  | Forum |  | Purpose | Inputs cut-off | Outputs | Approvals | Actions tracked where?
2.5 | Template 2.5 — Minimum Publication Standard (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Cut-off and freeze window stated
Version ID present
Reviewer and approver recorded
Key measures traceable to systems-of-record
Limitations declared where evidence is insufficient
Distribution controlled (audience variants)
Evidence index reference included
2.6 | Template 2.6 — NC Service Catalogue (starter)
Service |  | Decision supported |  | Cadence | Owner | Outputs | Evidence standard | Status (draft/live)
2.7 | Template 2.7 — First-Wave Service Implementation Plan
FIELD / CONTROL |  |  | WORKING ENTRY
Service selected:
Why this first (value + controllability):
Dependencies (definitions, identifiers, cut-offs):
Gates required:
Shadow mode plan (if used):
Training required:
Go-live criteria:
2A | Checklist 2A — NC conversion readiness
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | We can list the key decisions our governance forums must make
□ | Each decision has a named owner and an identified option window
□ | We can define decision services (inputs → validations → outputs → gates)
□ | We have a draft service catalogue with accountable service owners
□ | We have a cadence map that includes fast triage and formal governance
□ | We have a minimum publication standard and can apply it consistently
2B | Checklist 2B — Service design quality gate (before build)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Service purpose is decision-led (not report-led)
□ | Inputs are controllable (systems-of-record, cut-offs)
□ | Definitions and thresholds have owners
□ | Confidentiality classification and audience variants are defined
□ | Gates are explicit (review/approve/publish)
□ | Evidence bundle expectations are defined
□ | Outputs end in actions/decisions (not commentary)
2C | Checklist 2C — Anti-patterns to stop immediately
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | “Single version of truth” as a meeting argument (instead of ownership and rules)
□ | Packs without cut-offs, versions, or approvals
□ | Narrative that implies causation without evidence
□ | Local AI assistants generating governance narratives outside gates
□ | Exceptions without owners and due dates
THE DECISION-GRADE PMO · COMPANION PACK · Ch02_From_Tools_to_Nerve_Cent

## Ch03_What_AI_Can_and_Cannot_D
Chapter 3 — What AI Can and Cannot Do in a PMO
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 6 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
3.1 | Template 3.1 — Service Card: AI Fit Assessment
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision supported and forum
Consequence level (low/medium/high)
Data sensitivity (internal/restricted)
Steps in the service (compile/validate/detect/draft/decide)
AI capability fit by step (automation/ML/GenAI/agent/none)
Allowed sources (systems-of-record; approved corpora)
Evidence rules (what must be referenced)
LoA by step (assist/recommend/route/publish)
Gates (review/approve/publish)
Logging required
Limitations and “do not use when…” conditions
Owner
3.2 | Template 3.2 — Task Classification Map
Service |  | Step |  | Task type (compile/validate/detect/draft/decide) |  | Candidate AI type | Human accountability point | Notes
3.3 | Template 3.3 — Level of Autonomy (LoA) Map
Service |  | Step |  | AI involvement | Human reviewer | Approver | Publication allowed? | Evidence required
3.4 | Template 3.4 — Evidence-led Output Rules (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Allowed inputs (structured fields and approved outputs only):
Required evidence references for key claims:
Prohibited behaviours (no invention, no causation without proof, no hidden assumptions):
Standard limitations block (when evidence is weak):
Reviewer checklist reference:
Where to route investigation actions:
3.5 | Template 3.5 — “Exploratory vs Governance” Labelling Rules
FIELD / CONTROL |  |  | WORKING ENTRY
Exploratory outputs (no approvals; internal only)
Governance outputs (cut-off, version, approvals, evidence index)
Labels and distribution rules
3.6 | Template 3.6 — AI Use Case Screen (go / no-go)
FIELD / CONTROL |  |  | WORKING ENTRY
Use case summary:
Decision supported:
Benefit mechanism (timeliness/quality/control strength/efficiency):
Data readiness (definitions stable? cut-offs? identifiers?):
Confidentiality risks and audience variants:
Evidence requirements:
Autonomy level proposed:
Gate requirements:
Recommendation: proceed / proceed with constraints / stop
3A | Checklist 3A — “Fit for governance” test
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Decision supported is defined and has an accountable owner
□ | Inputs are from systems-of-record and/or controlled documents
□ | Cut-off and versioning are explicit
□ | Key claims are evidence-linked (or limitations declared)
□ | Review and approval steps are defined
□ | Distribution is controlled (audience variants)
□ | Logging and retention are in place
3B | Checklist 3B — GenAI safety checklist (PMO context)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | GenAI is constrained to structured fields and approved corpora
□ | Narrative template removes unsupported causation
□ | “No evidence = say so” behaviour is tested
□ | Confidentiality and permissions are enforced
□ | Outputs are reviewed before governance publication
3C | Checklist 3C — Agent readiness checklist
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Workflow steps and gates are explicit
□ | Logging is sufficient to reconstruct what happened
□ | Safe mode and rollback are defined and owned
□ | Write-back is restricted (draft-only unless approved)
□ | Monitoring thresholds exist for validation failures
THE DECISION-GRADE PMO · COMPANION PACK · Ch03_What_AI_Can_and_Cannot_D

## Ch04_Governance_Accountabilit
Chapter 4 — Governance, Accountability, and Human-in-the-Loop
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
4.1 | Template 4.1 — Decision Rights and Publication Authority Map
Decision service |  | Decision owner |  | Pack/report owner | Reviewer(s) | Approver(s) | Publication permitted to (audience) | Notes
4.2 | Template 4.2 — Level of Autonomy (LoA) Map (by step)
Service |  | Step |  | AI role (none/assist/recommend/route/publish) | Human reviewer | Approver | Evidence required | Constraints
4.3 | Template 4.3 — Publication Gate Checklist (governance-facing outputs)
FIELD / CONTROL |  |  | WORKING ENTRY
Output name and period:
Cut-off stated and met:
Version IDs recorded (data/rules/prompts/templates):
Key measures traceable to sources:
Limitations declared where evidence is weak:
Reviewer recorded:
Approver recorded:
Audience variant applied:
Distribution recorded:
Evidence index reference stored:
4.4 | Template 4.4 — Audience Variant Rules (book-wide)
Variant (audience) |  | Information rights (what this audience may see) |  |  | Sections included / excluded / summarised, and why |  | Sensitive field handling | Version, approver and distribution log reference
Executive variant |  | Aggregated, decision-focused, minimal sensitive detail
Operational variant |  | Sufficient detail for action owners
Restricted variant |  | Commercial and people-sensitive content, tightly permissioned
4.5 | Template 4.5 — Segregation of Duties (SoD) Rules by Service
Service |  | High-consequence decision? |  | Roles requiring separation |  | Minimum reviewers |  | Notes
4.6 | Template 4.6 — Publication Record (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Output/pack ID and version
Cut-off timestamp
Inputs (systems-of-record references)
Rules/templates/prompts used (versions)
Exceptions/overrides (what, why, approved by)
Reviewed by / approved by (date/time)
Audience variant and distribution
Evidence index reference
4.7 | Template 4.7 — Safe Mode Triggers (service-level)
FIELD / CONTROL |  |  | WORKING ENTRY
Trigger (what fails):
Threshold:
Immediate action (pause/revert/label exploratory):
Who can trigger:
Who must be informed:
Evidence to preserve:
4.8 | Template 4.8 — Governance-facing AI Output Rules (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Allowed sources (systems-of-record and controlled documents):
Prohibited behaviours (no invention; no causation without evidence; no hidden assumptions):
Required evidence references:
Standard limitations block:
Separation of facts vs interpretation:
Escalation route for evidence gaps:
4A | Checklist 4A — Governance readiness for AI-enabled NC services
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Decision owners and publishing owners are explicit per service
□ | LoA is defined by step (assist/recommend/route/publish)
□ | Publication Gate exists and is mandatory for governance use
□ | Governance-facing output rules prevent invention and require evidence
□ | SoD rules exist for high-consequence services
□ | Permissions and audience variants are designed-in
□ | Logging and retention expectations are defined
□ | Safe mode triggers and escalation routes are agreed
4B | Checklist 4B — Approval quality gate (before governance use)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Output is decision-led (exceptions/options/decisions/actions)
□ | Key measures are traceable to sources-of-record
□ | Limitations are declared where evidence is weak
□ | Reviewer and approver are recorded
□ | Distribution is correct and logged
4C | Checklist 4C — Preventing autonomy creep
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | LoA is reviewed on a cadence
□ | “Do not use when…” conditions exist for signals
□ | Publishing rights are controlled
□ | Prompt/template changes are versioned and approved
THE DECISION-GRADE PMO · COMPANION PACK · Ch04_Governance_Accountabilit

## Ch05_Data_Readiness_and_Evide
Chapter 5 — Data Readiness and Evidence Standards
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 7 TEMPLATES · 2 CHECKLISTS |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
5.1 | Template 5.1 — Decision-Critical Data Inventory
FIELD / CONTROL |  | WORKING ENTRY
Data category
KDE
Definition reference
System-of-record
Owner
Cut-off
Quality rule summary
Notes
5.2 | Template 5.2 — Identifier and Coding Standard (lightweight)
FIELD / CONTROL |  | WORKING ENTRY
Project/programme ID rules
Work breakdown alignment (WBS/CBS mapping approach)
Work package/activity ID rules
Change ID rules and linkage requirements
Risk/issue ID rules and linkage requirements
Supplier/contract ID rules (if relevant)
Naming conventions
Exceptions process
5.3 | Template 5.3 — Metric Definition Sheet (one per critical metric)
FIELD / CONTROL |  | WORKING ENTRY
Metric name
Business meaning (one sentence)
Formula / derivation rules (plain English)
Inputs (fields and sources)
System-of-record
Cut-off and frequency
Owner
Known limitations / exclusions
Typical failure modes
Approval route
5.4 | Template 5.4 — KDE Quality Rules and Thresholds
FIELD / CONTROL |  | WORKING ENTRY
KDE
Completeness rule
Validity rule
Consistency rule
Timeliness rule
Threshold
Exception owner
Escalation route
5.5 | Template 5.5 — Evidence Index and Lineage Log (minimum viable)
FIELD / CONTROL |  | WORKING ENTRY
Output name
Reporting period and cut-off
Output version ID
Source extracts used (system, dataset ID, timestamp)
Transformations applied (rule set version; key mappings)
Exceptions and overrides (what changed, why, approved by)
Evidence pack index reference (Template 5.7 ID)
Prepared by / reviewed by / approved by (with dates)
Distribution record (where published and to whom)
5.6 | Template 5.6 — Data Issue Record (for recurring problems)
FIELD / CONTROL |  | WORKING ENTRY
Issue ID
Description
Impacted decisions/outputs
Root cause hypothesis
Owner
Immediate containment
Corrective action
Due date
Status
Evidence of closure
5.7 | Template 5.7 — Evidence Pack Index (controlled)
FIELD / CONTROL |  | WORKING ENTRY
Evidence Pack ID
Related output / decision (pack ID)
Period / cut-off
Output version ID
Evidence item ID
Evidence type
Title / description
Owner
Date
Source location
Version / revision
Access classification
Permission notes
Notes
5A | Checklist 5A — Minimum data readiness for NC services
DONE | CONTROL / STANDARD |  | EVIDENCE / NOTES
□ | Decision-critical dataset identified (not everything)
□ | System-of-record agreed per critical measure
□ | Metric owners assigned and definition sheets maintained
□ | Minimum identifiers and mappings defined (WBS/CBS, change IDs, risk IDs)
□ | Reporting cut-offs and freeze windows agreed
□ | KDE quality rules and thresholds defined
□ | Exception handling route and escalation defined
□ | Evidence index/lineage log implemented for published packs
□ | Evidence pack index in place and routinely referenced
5B | Checklist 5B — Evidence standard for governance packs
DONE | CONTROL / STANDARD |  | EVIDENCE / NOTES
□ | Cut-off stated on the pack
□ | Version ID present
□ | Key measures trace to system-of-record references
□ | Transformations and mappings documented and versioned
□ | Overrides logged with rationale and approval
□ | Reviewer and approver recorded
□ | Evidence pack index reference included
THE DECISION-GRADE PMO · COMPANION PACK · Ch05_Data_Readiness_and_Evide

## Ch06_Designing_the_PMO_Operat
Chapter 6 — Designing the PMO Operating Process for AI
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 7 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
6.1 | Template 6.1 — Decision Service Card (operating design)
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision supported and forum
Decision owner
Service owner
Cadence (weekly/monthly/stage-gate)
Option window
Inputs (systems-of-record / controlled outputs)
Cut-offs and freeze window
Validations (KDE, reasonableness)
Outputs (exceptions/options/pack/logs)
Gates (review/approve/publish)
Evidence index requirements
Confidentiality classification and audience variants
LoA by step
Safe mode triggers
6.2 | Template 6.2 — Service Workflow Map
FIELD / CONTROL |  |  | WORKING ENTRY
Step
Input(s)
Validation(s)
Output(s)
Owner
AI role (if any)
Gate/approval
Evidence/log
6.3 | Template 6.3 — LoA Map by Service Step
Service |  | Step |  | AI role (assist/recommend/route/publish) | Human review | Human approval | Publication allowed? | Notes
6.4 | Template 6.4 — Evidence-led Output Rules (service-level)
FIELD / CONTROL |  |  | WORKING ENTRY
Allowed sources:
Required evidence references:
Prohibited behaviours (no invention; no causation without evidence):
Standard limitations block:
Evidence gap routing (to actions):
Reviewer checklist reference:
6.5 | Template 6.5 — Service Runbook (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Service purpose and scope
Cadence and cut-offs
Step-by-step procedure
Roles and cover arrangements
Validation checks and thresholds
Gates and approvals
Logging and retention requirements
Distribution rules (audience variants)
Safe mode triggers and actions
Escalation routes
6.6 | Template 6.6 — NC Cadence Map (two-speed)
Cycle |  | Horizon |  | Inputs cut-off | Outputs | Decision/action expectations | Forum | Owner
6.7 | Template 6.7 — Service Go-Live Criteria
FIELD / CONTROL |  |  | WORKING ENTRY
Inputs meet KDE thresholds:
Cut-offs operational:
Publication Gate checklist in use:
Evidence index and versioning tested:
Reviewer/approver roles trained:
Confidentiality variants tested:
Safe mode and incident route tested:
Shadow mode results reviewed (if used):
6A | Checklist 6A — Embed AI into the operating process (service-level)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Service is decision-led with named decision owner and service owner
□ | Workflow steps are explicit (inputs → validations → outputs)
□ | Cut-offs and freeze windows defined
□ | Gates exist (review/approve/publish) and are mandatory
□ | LoA map exists by step and prevents autonomy creep
□ | Evidence-led output rules are defined and used
□ | Runbook exists and is operable (roles, cover, escalation)
□ | Action/decision loop is linked to pack versions and evidence index
6B | Checklist 6B — Publication Gate (before governance use)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Inputs meet KDE thresholds (or limitations declared)
□ | Cut-off stated; late changes disclosed
□ | Output version recorded
□ | Key measures and claims are traceable
□ | Evidence index completed and stored
□ | Reviewer and approver recorded
□ | Audience variant and distribution correct
6C | Checklist 6C — Exception triage hygiene
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Materiality thresholds defined
□ | Exceptions have owners and due dates
□ | False alarms and noise are reviewed and thresholds adjusted
□ | Exceptions escalate to options papers when decision is required
THE DECISION-GRADE PMO · COMPANION PACK · Ch06_Designing_the_PMO_Operat

## Ch07_AI_in_Integrated_Plannin
Chapter 7 — AI in Integrated Planning and Scheduling
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 7 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
7.1 | Template 7.1 — Schedule Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision(s) supported
Decision owner
Service owner
Cadence (weekly triage / monthly governance / stage-gate)
Horizon (near-term focus)
Inputs and cut-offs
Schedule quality checks used (rule set version)
Early warning signals used
Outputs (exceptions/options/pack/logs)
Gates (review/approve/publish)
Evidence index requirements
Safe mode triggers
7.2 | Template 7.2 — Schedule Quality Exception Report (structure)
FIELD / CONTROL |  |  | WORKING ENTRY
Exception type
ID(s)
Location (WBS/WP)
Why it matters
Threshold breached
Owner
Due
Notes
7.3 | Template 7.3 — Schedule Health Scorecard (owned definitions)
Measure |  | Definition reference |  | Current |  | Trend | Threshold | Commentary (evidence-led)
7.4 | Template 7.4 — Exception Triage Register (planning)
FIELD / CONTROL |  |  | WORKING ENTRY
Exception ID
Horizon (weeks)
Driver
Option window
Owner
Options required by
Next forum
Evidence refs
7.5 | Template 7.5 — Planning Options Paper (schedule-led)
FIELD / CONTROL |  |  | WORKING ENTRY
Exception / decision required:
Cut-off and schedule version:
What changed (activity IDs/milestones):
Drivers (facts) and evidence refs:
Option A:
plan changes (IDs):
impacts (time/cost/risk/resource):
dependencies/constraints:
residual risks:
Option B:
Option C:
Recommendation (if appropriate) and what would change it:
Approvals required:
7.6 | Template 7.6 — Assumptions and Constraints Log (planning)
ID |  | Assumption/constraint |  | Applies to (WBS/WP/ID) | Source/evidence | Owner | Valid until | Status
7.7 | Template 7.7 — Baseline and Replan Decision Record
FIELD / CONTROL |  |  | WORKING ENTRY
Baseline/rebaseline requested
Reason and triggers
Scope included/excluded
Evidence summary and key limitations
Approvals
Effective date and version references
7A | Checklist 7A — Schedule quality gate (minimum viable)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Status date and cut-off are explicit
□ | Logic is sufficient for critical work (no open ends)
□ | Constraints are justified and within policy
□ | Calendars are applied correctly
□ | Lags/leads are within governed thresholds (or justified)
□ | Progress updates are consistent (no out-of-sequence anomalies)
□ | Exception report produced and routed to owners
7B | Checklist 7B — Option paper quality gate (planning)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Option window is stated
□ | Option changes are tied to specific plan IDs
□ | Impacts cover time/cost/risk/resource (or limitations declared)
□ | Dependencies and constraints are explicit
□ | Evidence references exist for key claims
□ | Recommendation is contestable (“what would change it”)
□ | Approvals required are identified
7C | Checklist 7C — Preventing schedule theatre
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Governance pack starts with exceptions and decisions required
□ | Trends are explained via drivers, not adjectives
□ | Replans and baselines are decision-recorded and approved
□ | Late changes after cut-off are disclosed and trended
THE DECISION-GRADE PMO · COMPANION PACK · Ch07_AI_in_Integrated_Plannin

## Ch08_AI_in_Cost_and_Estimatin
Chapter 8 — AI in Cost and Estimating
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 9 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
8.1 | Template 8.1 — Estimating Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision(s) supported
Decision owner
Service owner
Cadence (stage gate / monthly integrity)
Inputs and cut-offs
Estimate structure standard (CBS/WBS mapping)
Quality checks (rule set version)
Benchmarking approach (if used)
Outputs (model, BoE, exceptions, options, logs)
Gates (review/approve/publish)
Evidence index requirements
Confidentiality variants
Safe mode triggers
8.2 | Template 8.2 — Basis of Estimate (BoE) Summary (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Scope inclusions
Scope exclusions
Estimating approach
Key quantities and sources
Key rates/productivity assumptions and sources
Allowances (overheads, escalation/inflation, risk allowances)
Contingency approach and governance
Key constraints/dependencies
Known limitations and maturity
Approvals required
8.3 | Template 8.3 — Assumption Register (controlled)
FIELD / CONTROL |  |  | WORKING ENTRY
Assumption ID
Category (qty/rate/productivity/escalation/strategy)
Statement
Source/evidence
Owner
Valid until
Impact if wrong
Status
8.4 | Template 8.4 — CBS/WBS Mapping Rules (versioned)
FIELD / CONTROL |  |  | WORKING ENTRY
Mapping rule set version
Scope mapping principles
Exceptions policy
Known gaps and workarounds
Approval route
8.5 | Template 8.5 — Estimate Quality Exception Report
FIELD / CONTROL |  |  | WORKING ENTRY
Exception type
CBS/WBS location
Item ID
Why it matters
Threshold
Owner
Due
Evidence refs
8.6 | Template 8.6 — Benchmark and Anomaly Triage List
FIELD / CONTROL |  |  | WORKING ENTRY
Item
Assumption type
Observed value
Comparator basis
Why flagged
Action required
Owner
Due
8.7 | Template 8.7 — Cost Uncertainty and Allowance Statement
FIELD / CONTROL |  |  | WORKING ENTRY
Base estimate definition
Allowances included (what and why)
Contingency definition and governance
Linkage to risk register and QRA (if used)
Material sensitivities
Limitations
8.8 | Template 8.8 — Estimate Evidence Index (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Estimate/model version ID
Cut-off and timestamp
Sources for quantities
Sources for rates/productivity
Mapping rule set version
Approved changes included/excluded
Overrides and approvals
Reviewer/approver record
Distribution record
8.9 | Template 8.9 — Estimate-to-Forecast Integrity Exceptions
Period |  | Forecast movement driver |  | Linked assumption/change ID | Materiality | Action (validate/change request/accept) | Owner | Evidence refs
8A | Checklist 8A — Estimate publish gate (governance-facing)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Scope inclusions/exclusions are explicit
□ | BoE summary exists and is consistent with model
□ | Key quantities have source references
□ | Key rates/productivity assumptions have sources and owners
□ | CBS/WBS mapping rules are versioned and retrievable
□ | Quality exception report reviewed and actions assigned
□ | Allowances/contingency approach is defined and governed
□ | Model version and cut-off recorded
□ | Evidence index completed
□ | Reviewer and approver recorded; distribution controlled
8B | Checklist 8B — Assumption control (preventing hidden bias)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | All material assumptions are in the register
□ | Each assumption has an owner and evidence reference
□ | Expiry/validity dates exist for market and productivity assumptions
□ | Impact-if-wrong is recorded for high-sensitivity assumptions
□ | Decisions accepting aggressive assumptions are recorded
8C | Checklist 8C — Monthly estimate-to-forecast integrity
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Forecast movements are reconciled to controlled drivers
□ | Changes link to change IDs and approvals where applicable
□ | Material movements trigger an options paper or estimate change request
□ | Assumption validity is reviewed (rates, productivity, escalation)
□ | Evidence index updated for major changes
THE DECISION-GRADE PMO · COMPANION PACK · Ch08_AI_in_Cost_and_Estimatin

## Ch09_AI_in_Risk_Management_an
Chapter 9 — AI in Risk Management and Quantitative Risk Analysis
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
9.1 | Template 9.1 — Risk Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision(s) supported
Decision owner
Service owner
Cadence (weekly triage / monthly governance / stage-gate)
Inputs and cut-offs
Hygiene checks and thresholds
Signals used (triage)
Outputs (triage, options, QRA where used)
Gates (review/approve/publish)
Evidence index requirements
Confidentiality variants
Safe mode triggers
9.2 | Template 9.2 — Risk Hygiene Exception Report
Risk ID |  | Exception type (owner/date/linkage/mitigation) |  | Why it matters | Owner | Due | Escalation | Notes
9.3 | Template 9.3 — Risk Triage Register (weekly)
FIELD / CONTROL |  |  | WORKING ENTRY
Item
Type (risk/issue/assumption)
Horizon
Trigger (score/signal/ageing)
Owner
Option window
Next step
Evidence refs
9.4 | Template 9.4 — Risk Hypothesis Log
FIELD / CONTROL |  |  | WORKING ENTRY
Hypothesis ID
Statement (hypothesis)
Evidence supporting
Evidence missing
Validation action
Owner
Due
Status
9.5 | Template 9.5 — Risk Options Paper
FIELD / CONTROL |  |  | WORKING ENTRY
Risk/issue statement and ID
Cut-off and pack version
Evidence summary (what we know)
Hypotheses and gaps (what we do not know)
Option A (mitigate) |  |  | costs, schedule impacts, dependencies, residual risk
Option B (transfer/contract)
Option C (avoid/change strategy)
Option D (accept) |  |  | residual risk and acceptance authority
Recommendation (if appropriate) and what would change it
Approvals required
9.6 | Template 9.6 — QRA Readiness Gate (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Decision question to answer
Baseline snapshot and cut-off
Scope of quantification
Inputs required (risk list, distributions, correlations)
Rationale for distributions (evidence)
Correlation assumptions and rationale
Configuration/version control plan
Interpretation plan (how results will be used)
Approval to proceed
9.7 | Template 9.7 — QRA Input Pack (controlled)
FIELD / CONTROL |  |  | WORKING ENTRY
Input dataset references (IDs, timestamps)
Risk mapping to model elements (WBS/milestones/cost items)
Distributions and parameters (with evidence references)
Correlations (with rationale)
Model configuration version
Review/approval record
9.8 | Template 9.8 — Residual Risk Acceptance Record
FIELD / CONTROL |  |  | WORKING ENTRY
Risk/issue ID
Decision being made
Residual exposure summary
Evidence references and limitations
Acceptance decision owner
Date and forum
Review date / validity conditions
9A | Checklist 9A — Risk service publish gate (governance-facing)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Risk statements are clear, owned, and current
□ | Review dates are current and overdue items are escalated
□ | Mitigations are costed/scheduled where required (or limitations declared)
□ | Linkages to plan/cost/change exist for material items
□ | Hypotheses are labelled; causation is not asserted without evidence
□ | Decisions and actions are recorded and linked to pack version
□ | Evidence index references are present for key items
□ | Audience variants and distribution controls applied
9B | Checklist 9B — QRA quality and defensibility
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | The decision question is explicit (why are we quantifying?)
□ | Baseline snapshot and cut-off are defined and stable
□ | Distributions have evidence or rationale; assumptions are versioned
□ | Correlations are addressed where material
□ | Configuration and inputs are reproducible (versioned)
□ | Results include an interpretation note and limitations
□ | Approval and publication records exist
9C | Checklist 9C — Preventing risk theatre
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Weekly triage exists and protects option windows
□ | Risk discussions end in options, decisions, and actions
□ | Overdue mitigations are treated as exceptions
□ | Accepted risks are explicitly accepted and periodically revalidated
THE DECISION-GRADE PMO · COMPANION PACK · Ch09_AI_in_Risk_Management_an

## Ch10_AI_in_Change_and_Contrac
Chapter 10 — AI in Change and Contract Management
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
10.1 | Template 10.1 — Change Record Standard (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Change ID |  |  | Unique, immutable
Origin/date raised |  |  | Mandatory
Description and location |  |  | WBS/work package reference
Status |  |  | Draft / submitted / under review / approved / rejected
Owner |  |  | Named
Required approvals |  |  | Named roles and current approver
Requested impacts |  |  | Time / cost / resources (ranges allowed)
Assumptions |  |  | Linked to assumptions log
Linkages |  |  | Schedule IDs, cost codes, risk IDs, instruction refs
Evidence references |  |  | Controlled output IDs
Deadlines |  |  | Notice/response dates (if applicable)
10.2 | Template 10.2 — Change Triage Register (weekly)
FIELD / CONTROL |  |  | WORKING ENTRY
Change ID
Category
Ageing
Deadline risk
Materiality
Owner
Next action
Option window
Evidence gap?
10.3 | Template 10.3 — Change Exposure Register (approved/pending/emerging)
Period |  | Approved impact (time/cost) |  | Pending exposure (range) |  | Emerging signals (summary) | Confidence/limitations | Decisions required
10.4 | Template 10.4 — Instruction Register
FIELD / CONTROL |  |  | WORKING ENTRY
Ref
Date
Issuer
Recipient
Instruction summary
Linked change ID(s)
Evidence location
Notes
10.5 | Template 10.5 — Notice and Response Tracker
FIELD / CONTROL |  |  | WORKING ENTRY
Ref
Related change/issue
Notice type
Deadline
Responsible owner
Status
Evidence ref
Escalation
10.6 | Template 10.6 — Cumulative Impact Register (change integration)
Work package/WBS |  | Number of changes |  | Approved impact | Pending impact range | Key assumptions | Linked risks | Decision trigger
10.7 | Template 10.7 — Change Options Paper (governance)
FIELD / CONTROL |  |  | WORKING ENTRY
Change ID and summary
Cut-off and pack version
Evidence summary (facts and references)
Impact assessment (time/cost/risk/resource)
Uncertainty and limitations
Option A (approve as is)
Option B (approve with conditions)
Option C (reject/alternative scope)
Option D (defer with risk acceptance)
Approvals required
10.8 | Template 10.8 — Commercial Position Evidence Pack Index
FIELD / CONTROL |  |  | WORKING ENTRY
Change/issue ID
Contract clause references (sections)
Instruction references
Notice/response references
Impact assessment outputs
Decision records and approvals
Correspondence log references
Limitations/gaps and actions
10A | Checklist 10A — Change service publish gate (governance-facing)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Change IDs are unique and statuses are current
□ | Required approvals and current approver are visible
□ | Ageing and deadline exceptions are highlighted
□ | Material impacts have linkage to schedule/cost and assumptions are recorded
□ | Evidence references are indexed and retrievable
□ | Uncertainty is stated (ranges/limitations) where applicable
□ | Audience variants and distribution controls applied
□ | Decisions and actions are linked to pack version and evidence index
10B | Checklist 10B — Notice and instruction discipline
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Instruction register is current and referenced
□ | Notice deadlines are tracked with owners
□ | Issued notices/responses are stored and indexed
□ | Any classification judgement (notice vs clarification) is recorded and owned
□ | Escalation route exists for imminent deadline risk
10C | Checklist 10C — Preventing change theatre
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Weekly triage exists and focuses on options and deadlines
□ | Exposure view (approved/pending/emerging) is maintained
□ | Cumulative impact is reviewed routinely
□ | Evidence pack completeness is sampled for top material items
THE DECISION-GRADE PMO · COMPANION PACK · Ch10_AI_in_Change_and_Contrac

## Ch11_AI_in_Resource_and_Capab
Chapter 11 — AI in Resource and Capability Management
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 10 TEMPLATES · 4 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
11.1 | Template 11.1 — Resource Decision Service Card
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision(s) supported
Decision owner
Service owner
Cadence (weekly triage / monthly capability)
Horizon
Inputs and cut-offs
Demand capture standard
Capacity modelling assumptions
Scenario approach (if used)
Outputs (exceptions/options/decisions/actions)
Gates (review/approve/publish)
Evidence index requirements
Confidentiality classification and audience variants
Safe mode triggers
11.2 | Template 11.2 — Demand Register (controlled)
FIELD / CONTROL |  |  | WORKING ENTRY
Demand ID
Work package / milestone ID
Role/skill
Start
End
Effort (range)
Priority (approved)
Decision owner
Status
Evidence refs
11.3 | Template 11.3 — Demand Quality Exception Report
Demand ID |  | Exception (missing link/skill/dates/priority) |  | Why it matters |  | Owner | Due | Notes
11.4 | Template 11.4 — Capacity Profile (role/skill)
Role/skill |  | Time window |  | Available capacity |  | Committed capacity | Constraint notes | Assumption refs
11.5 | Template 11.5 — Capacity Assumptions Log
ID |  | Assumption |  | Applies to | Rationale/evidence | Owner | Valid until | Status
11.6 | Template 11.6 — Demand–Capacity Triage Register (weekly)
FIELD / CONTROL |  |  | WORKING ENTRY
Exception ID
Role/skill
Time window
Impacted work package IDs
Option window
Owner
Options required by
Next forum
Evidence refs
11.7 | Template 11.7 — Resource Options Paper (constraint-driven)
FIELD / CONTROL |  |  | WORKING ENTRY
Constraint/exception summary:
Cut-off and snapshot versions:
Evidence summary (facts and references):
Uncertainty and limitations:
Option A (re-sequence): impacts and dependencies:
Option B (add capacity): cost/time implications and lead time:
Option C (defer/descoped): benefits and residual impacts:
Option D (accept overload risk): residual risks and acceptance authority:
Recommendation (if appropriate) and what would change it:
Approvals required:
11.8 | Template 11.8 — Scenario Comparison Table
Scenario |  | What changes |  | Demand–capacity position | Schedule impact summary | Cost impact summary | Risk implications | Limitations
11.9 | Template 11.9 — Capability Gap and Action Plan
FIELD / CONTROL |  |  | WORKING ENTRY
Gap (role/skill)
Drivers (demand sources)
Options (build/buy/borrow)
Decision required
Owner
Due date
Status
Evidence refs
11.10 | Template 11.10 — Audience Variant Rules (people data)
FIELD / CONTROL |  |  | WORKING ENTRY
Executive forum variant (role-level only; no individual data)
Delivery management variant (role/team level as permitted)
Restricted variant (named individuals where explicitly approved and permissioned)
Redaction rules
Distribution logging requirements
11A | Checklist 11A — Resource service publish gate (governance-facing)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Demand register is cut at an agreed cut-off; version recorded
□ | Capacity snapshot cut-off and version recorded
□ | Role/skill taxonomy and mapping versions recorded
□ | Material exceptions are prioritised by horizon and option window
□ | Options papers exist for decisions required
□ | Assumptions and limitations are explicit (ranges where needed)
□ | Reviewer/approver recorded; decisions/actions logged
□ | Audience variants applied; distribution controlled and logged
11B | Checklist 11B — Demand quality and comparability
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Each demand entry has work package/milestone linkage
□ | Role/skill is coded to the taxonomy
□ | Start/end dates are present and realistic
□ | Effort is stated as a range where uncertain
□ | Priority and decision owner are explicit
□ | Evidence references exist for the request and approval
11C | Checklist 11C — Bias and confidentiality controls
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Outputs remain at role/skill level unless explicitly approved otherwise
□ | Access controls align to data sensitivity
□ | Model recommendations are reviewed for fairness and policy alignment
□ | Redaction rules are applied for broader distribution
□ | Incident route and safe mode triggers exist
11D | Checklist 11D — Scenario hygiene
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Scenario is defined as explicit changes, not a narrative
□ | Assumptions are listed and versioned
□ | Impacts are summarised across schedule/cost/risk where available
□ | Limitations and confidence are declared
□ | Decision and review date are recorded
THE DECISION-GRADE PMO · COMPANION PACK · Ch11_AI_in_Resource_and_Capab

## Ch12_AI_in_Reporting_Performa
Chapter 12 — AI in Reporting, Performance, and Insight
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 4 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
12.1 | Template 12.1 — Governance Pack Spine (standard structure)
FIELD / CONTROL |  |  | WORKING ENTRY
Cover |  |  | period, cut-off, version, pack owner, approver
Section 1 |  |  | Decisions required (with option papers)
Section 2 |  |  | Exceptions summary (by domain)
Section 3 |  |  | Options and recommendations (with limitations)
Section 4 |  |  | Performance measures (trend and drivers)
Section 5 |  |  | Risk and change exposure (decision-led)
Section 6 |  |  | Actions and follow-through (overdue beyond tolerance)
Section 7 |  |  | Evidence index references and publication record
12.2 | Template 12.2 — Exception-to-Decision Mapping
Exception type |  | Threshold |  | Typical decisions triggered | Required option fields |  | Owner role
12.3 | Template 12.3 — Variance Narrative Template (evidence-led)
FIELD / CONTROL |  |  | WORKING ENTRY
Topic (schedule/cost/risk/change/resource):
Cut-off and data versions used:
Facts (what changed) with evidence refs:
Interpretation (what it may mean) – label uncertainty:
Options (A/B/C) with trade-offs:
Recommendation (if appropriate) and what would change it:
Limitations (insufficient evidence / assumptions / confidence):
Actions and owners:
12.4 | Template 12.4 — Options Paper (generic, decision-grade)
FIELD / CONTROL |  |  | WORKING ENTRY
Decision required:
Trigger/exceptions and thresholds:
Evidence summary:
Option A:
Option B:
Option C:
Risks and mitigations:
Dependencies and constraints:
Cost/schedule/resource impacts (or limitations):
Recommendation and decision route:
12.5 | Template 12.5 — Publication Record (reporting)
FIELD / CONTROL |  |  | WORKING ENTRY
Pack ID and version
Cut-off timestamp
Inputs used (dataset IDs and timestamps)
Rule set / template / prompt versions
Overrides and approvals
Reviewed by / approved by (date/time)
Audience variant and distribution log reference
Evidence index reference
12.6 | Template 12.6 — Weekly Insight Brief (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
What changed (top exceptions)
Why it matters (decision relevance)
Option windows (what is closing)
Decisions needed and by when
Actions assigned and overdue
Limitations and evidence gaps
12.7 | Template 12.7 — Measures and Thresholds Catalogue (owned)
Measure |  | Definition reference |  | Threshold/tolerance | Decision relevance | Owner | Change control route
12.8 | Template 12.8 — Audience Variant Rules (reporting)
FIELD / CONTROL |  |  | WORKING ENTRY
Executive variant (aggregated; no sensitive detail)
Delivery variant (operational detail as permitted)
Restricted commercial variant (supplier/contract detail)
Restricted people variant (only with explicit permission)
Redaction rules and distribution logging
12A | Checklist 12A — Reporting service publish gate (governance-facing)
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Pack purpose and decisions required are explicit
□ | Cut-off stated and met; pack version recorded
□ | Key measures trace to systems-of-record references
□ | Exceptions are prioritised by materiality and option window
□ | Narratives follow the evidence-led template (facts vs interpretation vs options)
□ | Limitations and evidence gaps are declared and routed
□ | Reviewer and approver recorded
□ | Audience variant applied; distribution controlled and logged
□ | Evidence index reference included; publication record completed
12B | Checklist 12B — Narrative quality (anti-hallucination)
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | No unsupported causation or commitments
□ | Evidence references exist for key claims
□ | Uncertainty is labelled; assumptions are explicit
□ | Options include trade-offs and dependencies
□ | Actions have owners and due dates
12C | Checklist 12C — Exception hygiene
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Thresholds are calibrated and owned
□ | Exceptions are triaged (noise removed)
□ | Repeated exceptions are escalated as systemic issues
□ | Exception closure is tracked (did we resolve, mitigate, accept?)
12D | Checklist 12D — Action and decision follow-through
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Decisions are logged and linked to pack versions
□ | Actions are controlled, owned, and dated
□ | Overdue actions beyond tolerance are escalated
□ | Outcomes are reviewed (did the intervention work?)
THE DECISION-GRADE PMO · COMPANION PACK · Ch12_AI_in_Reporting_Performa

## Ch13_Digital_Data_Architectur
Chapter 13 — Digital & Data Architecture for the Digital PMO
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
13.1 | Template 13.1 — Service-to-Data Architecture Map
FIELD / CONTROL |  |  | WORKING ENTRY
NC service
Inputs (system-of-record)
Data Products required
Transformations
Outputs
Cadence/cut-off
Evidence Spine requirements
Access classification
13.2 | Template 13.2 — Data Product Card (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Data Product name
Purpose and decisions supported
Owner
Source system(s) and extraction method
Schema (fields, definitions, identifiers)
Cut-off and refresh cadence
Quality thresholds (KDE rules)
Transformation rules reference (version)
Access classification and permitted audiences
Retention requirement
Known limitations
13.3 | Template 13.3 — Integration and Transformation Rules Register
FIELD / CONTROL |  |  | WORKING ENTRY
Rule set ID
Purpose
Inputs
Output
Mapping references
Version
Owner
Approval route
Notes
13.4 | Template 13.4 — Access and Classification Matrix
Data Product/output |  | Classification |  | Who can access | Restrictions | Audience variants | Logging requirement
13.5 | Template 13.5 — Evidence Spine Specification (what must be logged)
FIELD / CONTROL |  |  | WORKING ENTRY
Publication output ID and version
Cut-off timestamp
Dataset version references (per input)
Transformation rule set versions
Exception rule set versions
Drafting output versions (templates/prompts)
Retrieval sources (document IDs) and query references (if used)
Overrides and approvals
Reviewed by / approved by (date/time)
Distribution log reference
13.6 | Template 13.6 — Retrieval Boundary and Indexing Policy
FIELD / CONTROL |  |  | WORKING ENTRY
Approved corpus scope (what is included/excluded)
Sensitivity tagging rules
Permission model and filtering
Indexing/chunking rules (versioned)
Citation requirement (internal document IDs)
Data retention and deletion rules
Human review requirements for governance outputs
13.7 | Template 13.7 — Service Release and Change Control Plan (Digital & Data)
FIELD / CONTROL |  |  | WORKING ENTRY
Environments (build/test/operate)
Release cadence
Change control for rules/templates/prompts
Testing requirements (data quality, permissions, reproducibility)
Approval route
Rollback plan
Monitoring and incident response
13.8 | Template 13.8 — Submission Contract Specification
FIELD / CONTROL |  |  | WORKING ENTRY
Period and cut-off date
Datasets required this period (the defined set)
Fixed schema, field definitions and coding per dataset
Validation rules applied at source (completeness, validity, consistency, currency)
Metadata carried as properties (project, period, dataset, version, cut-off, owner, sign-off)
Named signatory per dataset, and date signed
Structure/template version in force, and the period it took effect from
Mapping rules where a project genuinely differs (under change control)
Exception route |  |  | what happens when a submission fails, and who owns the fix
Level of Autonomy declared for each automated step
13A | Checklist 13A — Minimum viable architecture for an AI-enabled NC
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | NC services are defined and decision-led
□ | Systems-of-record agreed for key measures (Chapter 5)
□ | Governed Data Products exist for critical domains
□ | Cut-offs, versioning, and lineage logging are operational
□ | Mapping rules are treated as controlled assets
□ | Access control and classification are defined and enforced
□ | Evidence Spine logging supports reproducibility
□ | Publication Gates and distribution logs exist for packs
□ | Retrieval boundaries are controlled (if using GenAI)
□ | Runbooks, safe mode triggers, and incident routes are in place
13B | Checklist 13B — Safe GenAI retrieval readiness
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Approved corpus defined with inclusions/exclusions
□ | Sensitivity tags applied and maintained
□ | Permission filtering works for all audiences
□ | Outputs cite internal document IDs used
□ | Retrieval and drafting events are logged
□ | Human review is mandatory for governance-facing outputs
13C | Checklist 13C — Integration resilience
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Governed submission is the standing interface: defined set per period, fixed shape, signed before use
□ | Extract–validate–publish pattern is used
□ | Transformation rules are versioned and owned
□ | Pipeline failures trigger alerts and safe mode
□ | Manual workarounds are tracked and retired
THE DECISION-GRADE PMO · COMPANION PACK · Ch13_Digital_Data_Architectur

## Ch14_Assurance_Compliance_and
Chapter 14 — Assurance, Compliance, and Audit in an AI Context
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
14.1 | Template 14.1 — Assurance Scope Matrix
FIELD / CONTROL |  | WORKING ENTRY
NC service
Output type
Classification (governance/operational/exploratory)
Evidence standard required
Publication Gate required?
Retention
Owner
14.2 | Template 14.2 — Assurance Sampling Plan (minimum viable)
FIELD / CONTROL |  | WORKING ENTRY
Period and scope
Services included
Sample selection method (e.g., top material decisions + random)
Tests to run (reproducibility, evidence retrieval, permissions, overrides)
Acceptance criteria
Reporting route
Actions and escalation
14.3 | Template 14.3 — Control Test Log
FIELD / CONTROL |  | WORKING ENTRY
Test ID
Date
Service/output
Test performed
Pass/Fail
Findings
Action owner
Due
Evidence refs
14.4 | Template 14.4 — High-Consequence Decision Evidence Bundle Index
FIELD / CONTROL |  | WORKING ENTRY
Decision statement and owner
Forum/date
Options paper references
Data snapshots used (IDs, timestamps)
Rule sets / templates / prompt versions
Key assumptions and limitations
Approvals and publication record
Distribution record
Evidence pack index reference
14.5 | Template 14.5 — Control Incident Record (assurance-facing)
FIELD / CONTROL |  | WORKING ENTRY
Incident ID
What happened (facts)
Impacted outputs/decisions
Root cause hypothesis
Containment (including safe mode if needed)
Corrective action
Preventive action
Owner and due date
Closure evidence
14.6 | Template 14.6 — Segregation of Duties Map
FIELD / CONTROL |  | WORKING ENTRY
Service/output
Preparer
Reviewer
Approver
Compensating controls (if overlap)
14.7 | Template 14.7 — Control Improvement Backlog (controlled)
FIELD / CONTROL |  | WORKING ENTRY
Improvement ID
Source (incident/finding/audit)
Source ID
Control area/service
Issue statement (plain)
Risk/impact
Root cause category
Corrective action
Preventive action
Owner
Due date
Status
Closure evidence ref
Approver/date
Notes
14.8 | Template 14.8 — Rule/Prompt/Template Change Record
FIELD / CONTROL |  | WORKING ENTRY
Change ID
What changed (rule/prompt/template)
Reason
Impact assessment (comparability/confidentiality)
Test evidence
Approvals
Effective date and version
14A | Checklist 14A — Assurance-ready Publication Gate (governance outputs)
DONE | CONTROL / STANDARD |  | EVIDENCE / NOTES
□ | Output classification is governance-facing
□ | Cut-off stated and met; snapshot references recorded
□ | Output version ID recorded
□ | Transformation rule versions referenced
□ | Prompt/template versions referenced (where used)
□ | Overrides logged with rationale and approval
□ | Reviewer and approver recorded
□ | Audience variant applied and distribution logged
□ | Evidence index reference attached
14B | Checklist 14B — Audit Retrieval Checklist (retrieval readiness)
DONE | CONTROL / STANDARD |  | EVIDENCE / NOTES
□ | Pack version and publication record can be retrieved
□ | Data snapshot versions and timestamps can be retrieved
□ | Rule/prompt/template versions can be retrieved
□ | Evidence pack items can be retrieved under correct permissions
□ | Distribution record can be retrieved
□ | Decision and action logs are linked to the pack version
14C | Checklist 14C — GenAI output defensibility (narratives/options)
DONE | CONTROL / STANDARD |  | EVIDENCE / NOTES
□ | Inputs are restricted to approved sources and structured fields
□ | Key claims have evidence references
□ | Causation is not asserted without evidence
□ | Uncertainty and limitations are explicit
□ | Output is reviewed by a named reviewer
THE DECISION-GRADE PMO · COMPANION PACK · Ch14_Assurance_Compliance_and

## Ch15_Stakeholders_Communicati
Chapter 15 — Stakeholders, Communication, and Trust
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 7 TEMPLATES · 4 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
15.1 | Template 15.1 — Stakeholder Decision Map
Stakeholder group |  | Decisions owned/influenced |  | Information needed | Tolerance/thresholds | Cadence | Sensitivity constraints | Preferred outputs
15.2 | Template 15.2 — Trust Contract (NC Communication Charter)
FIELD / CONTROL |  |  | WORKING ENTRY
Purpose |  |  | what the NC communication service is for
Systems-of-record for key measures (by domain)
Cut-offs, freeze windows, and versioning approach
How AI is used (drafting/triage/synthesis) and how it is not used (deciding/judging)
Evidence behaviour |  |  | citation of internal references; “insufficient evidence” rule
Accountability |  |  | preparer/reviewer/approver expectations
Confidentiality |  |  | audience variants and distribution discipline
Challenge handling |  |  | how disputes are raised and resolved
15.3 | Template 15.3 — Standard Brief Format (facts → implications → options → decisions)
FIELD / CONTROL |  |  | WORKING ENTRY
Topic
Cut-off and version
Facts (evidence refs)
Implications (label uncertainty)
Options (A/B/C) with trade-offs
Decision required and by when
Actions and owners
Limitations and evidence gaps
15.4 | Template 15.4 — Stakeholder Q&A Brief
Likely question |  | Evidence-led answer |  | Evidence refs |  | Limitations / unknowns |  | Next action (if needed)
15.5 | Template 15.5 — Audience Variant Rules (communication)
FIELD / CONTROL |  |  | WORKING ENTRY
Executive variant |  |  | what is included/excluded
Operational variant |  |  | what is included/excluded
Restricted commercial variant |  |  | what is included/excluded
Restricted people variant |  |  | what is included/excluded
Redaction rules
Distribution logging requirements
15.6 | Template 15.6 — Challenge Log and Resolution Record
FIELD / CONTROL |  |  | WORKING ENTRY
Challenge ID
Raised by
Output/metric
Issue
Evidence requested
Owner
Resolution
Date
Notes
15.7 | Template 15.7 — Stakeholder Engagement Cadence Calendar
FIELD / CONTROL |  |  | WORKING ENTRY
Weekly triage touchpoints (attendees, agenda, outputs)
Monthly governance forums (pack deadlines, approval gates)
Stage-gate events (evidence bundle requirements)
Ad hoc escalation route and triggers
15A | Checklist 15A — Trust-ready communication (governance-facing)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Cut-off and version are visible
□ | Facts are separated from interpretation
□ | Key claims have evidence references
□ | Uncertainty and limitations are explicit
□ | Options and decision required are clear
□ | Reviewer and approver recorded (LoA aligned)
□ | Audience variant applied and distribution logged
□ | Decision/action follow-through is linked to the output
15B | Checklist 15B — GenAI drafting safety for stakeholder outputs
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Inputs restricted to approved structured fields and sources
□ | No implied commitments or entitlement assertions
□ | “Hypothesis vs fact” labels used where needed
□ | Limitations block included
□ | Human reviewer sign-off completed before publication
15C | Checklist 15C — Handling challenge and disagreement
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Confirm definition and cut-off before debating numbers
□ | Retrieve evidence index items for key claims
□ | Identify decision required and option window
□ | Record resolution in challenge log
□ | Escalate if dispute blocks decision beyond tolerance
15D | Checklist 15D — Audience and confidentiality
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Sensitivity classification applied to content
□ | Correct variant selected
□ | Redaction rules applied
□ | Distribution list authorised
□ | Distribution logged
THE DECISION-GRADE PMO · COMPANION PACK · Ch15_Stakeholders_Communicati

## Ch16_The_Predictive_PMO_in_Op
Chapter 16 — The Predictive PMO in Operation
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. These are starting points, not compliance forms.
CONTENTS: 6 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
16.1 | Template 16.1 — Predictive Capability Layer Assessment
Capability layer |  | Reactive symptom (today) |  | Predictive standard (target) | Current stage (1–5) | Gap / action | Owner
1. Clean data foundation |  |  |  | WBS/CBS aligned; percent complete calculated by rule; cut-off enforced
2. Predictive forecasting |  |  |  | EAC as trend line + P80 + stated methodology, not a point estimate
3. Risk prediction |  |  |  | Register linked to schedule at WBS level; leading indicators monitored
4. Resource and capacity forecasting |  |  |  | Integrated capacity view; critical disciplines identified; scenarios run
5. Governance intelligence |  |  |  | Exception-based triage; brief not alert; full-portfolio view retained
16.2 | Template 16.2 — Exception Brief (governance intelligence)
FIELD / CONTROL |  |  | WORKING ENTRY
Project / service
Signal (threshold-based or pattern-based)
Trend context
Options pre-framed
Decision authority
Next reporting cycle flagged
Evidence references (Evidence Spine)
Drafted by / approved by (discipline manager)
Publication Gate status
Level of Autonomy applied
16.3 | Template 16.3 — Alert Category Register
Alert category |  | Trigger / threshold |  | Named owner | Response window | Escalation path if unresolved | Auto-escalation rule
Unresolved across two consecutive digests escalates to the next governance cycle
16.4 | Template 16.4 — Predictive Forecast Presentation Standard
FIELD / CONTROL |  |  | WORKING ENTRY
Forecast (EAC or date)
Trend line (five periods)
Confidence basis (e.g. Monte Carlo P80)
Stated methodology note
Confidence score and its calculation basis
Limitations block (training basis, confidence basis, where data is thin)
Decision framed for the forum
Reviewer (named discipline manager)
Publication Gate status
16.5 | Template 16.5 — Model Card (governance-facing ML)
FIELD / CONTROL |  |  | WORKING ENTRY
Model name and NC service
What it was trained on
Performance metrics (precision, recall)
False positive rate (a governance metric)
Known limitations
Plain-English explanation of a flag
Review cadence
Owner
Last LoA review date
16.6 | Template 16.6 — Stage Progression Plan
Transition |  | Indicative duration |  | Critical path / gate criteria | Investment focus | Current status | Target date
Stage 1 → 2 (Reactive → Defined) |  | 6 to 12 months |  | CBS/WBS alignment is the critical path; scheduling procedure and cut-off discipline are the gate criteria | Data stewardship: a named owner per Data Product
Stage 2 → 3 (Defined → Analytical) |  | 3 to 6 months once the foundation is stable |  | Two to three full delivery cycles of consistent, coded data | Analytical capability and tool access
Stage 3 → 4 (Analytical → Predictive) |  | 6 to 18 months (most variable) |  | Pattern library: enough history across comparable contexts | Model development and governance
Stage 4 → 5 (Predictive → Autonomous) |  | Programme-dependent |  | Governance framework explicitly updated; track record documented; safe-mode triggers in place. LoA 3 applies | Only for mature operating environments
16A | Checklist 16A — Minimum viable predictive PMO (Stage 2 readers)
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | One clean, WBS-coded schedule Data Product
□ | One cost Data Product reconciled to finance monthly
□ | One named data steward per product
□ | A weekly exception report showing the five projects most at risk against both dimensions simultaneously
□ | Consistent inputs and a single integration point
□ | The discipline to maintain both
□ | Achievable in 90 days; no ML and no data pipeline required
16B | Checklist 16B — Before switching to exception-based governance
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Formal LoA governance review (Chapter 4) completed before deploying exception-based triage
□ | The transition made as an explicit governance decision, not by default
□ | Precision and recall demonstrated to the Board for the first three months
□ | Flagged correctly / missed / false-positived counts shown, not asserted
□ | Full-portfolio summary view maintained alongside the exception brief
16C | Checklist 16C — Control fabric maintenance (preventing Stage 3 atrophy)
New scope and subcontract mobilisations trigger a coding and procedure review before their data enters the portfolio set
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | WBS/CBS review cadence owned as a standing responsibility, not a project task
□ | Procedure update process owned and current
□ | Scheduling discipline audits scheduled and run
□ | Anomaly detection running on the data itself, not only on outputs
□ | Model performance metrics monitored, not just model outputs
THE DECISION-GRADE PMO · COMPANION PACK · Ch16_The_Predictive_PMO_in_Op

## Ch17_Building_the_Digital_PMO
Chapter 17 — Building the Digital PMO Roadmap
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 6 TEMPLATES · 4 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
17.1 | Template 17.1 — Service Prioritisation Backlog (roadmap)
FIELD / CONTROL |  |  | WORKING ENTRY
Service
Decision pain (what is late/disputed?)
Data readiness level
Risk/sensitivity
Expected decision impact
Effort (relative)
Recommended start?
Notes
17.2 | Template 17.2 — Thin Slice Charter (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Service name
Decision(s) improved
Decision owner
Service owner
Users and audiences
Output(s) to be published
In-scope Data Products and cut-offs
Controls and gates (publication, approvals, distribution)
Evidence Spine requirements
Success measures (non-vanity)
Risks and safe mode triggers
Timeline and resourcing
17.3 | Template 17.3 — Prerequisite Readiness Check (Phase 0)
FIELD / CONTROL |  |  | WORKING ENTRY
Decision owner named
Service owner named
System-of-record confirmed
Cut-off and freeze window workable
Minimum identifiers/mappings in place
Access classification and audience defined
Publication Gate agreed
Runbook owner identified
17.4 | Template 17.4 — Roadmap Release Plan (rules/prompts/templates)
Release |  | What changes (rules/prompts/templates) |  | Why | Tests required | Approver | Effective date | Rollback plan
17.5 | Template 17.5 — Gate Evidence Pack (for each phase gate)
FIELD / CONTROL |  |  | WORKING ENTRY
Gate ID (0/1/2/3)
Service
Evidence of prerequisites
Evidence of reproducibility
Evidence of approvals/distribution control
Evidence of stakeholder acceptance
Evidence of assurance sampling (where applicable)
Decision |  |  | proceed / hold / revert / remediate
17.6 | Template 17.6 — Adoption and Enablement Plan (service-led)
FIELD / CONTROL |  |  | WORKING ENTRY
Stakeholders and impacts:
Training needs and schedule:
Communication plan and variants:
Runbook and support model:
Feedback and improvement loop:
Risks and mitigations:
17A | Checklist 17A — Start gate (Gate 0)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Named decision owner and service owner
□ | Output type classified (governance/operational/exploratory)
□ | System-of-record agreed for critical measures
□ | Cut-off and freeze window defined
□ | Minimum identifiers/mappings exist (or are in scope for v1)
□ | Audience and confidentiality classification defined
□ | Publication Gate agreed for governance outputs
17B | Checklist 17B — Operability gate (Gate 1)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Data Product snapshotting/versioning works at cut-off
□ | Exception rules are owned, versioned, and producing useful signal
□ | Output is reproducible from the same snapshots
□ | Owners are acting on exceptions (follow-through)
□ | Approvals and distribution controls are functioning
17C | Checklist 17C — Credibility gate (Gate 2)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Constrained drafting uses approved sources only
□ | Citations and limitations blocks are present
□ | Human reviewer sign-off is consistent
□ | Stakeholders report improved clarity and comparability
□ | Evidence retrieval sampling passes (Chapter 12)
17D | Checklist 17D — Scale gate (Gate 3)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Assurance sampling passes routinely
□ | Safe mode triggers and rollback routes tested
□ | Role changes and capability uplift implemented (Chapter 18)
□ | Operating burden is reducing, not increasing
□ | Release/change control for rules/prompts/templates is working
THE DECISION-GRADE PMO · COMPANION PACK · Ch17_Building_the_Digital_PMO

## Ch18_Operating_Model_Roles_an
Chapter 18 — Operating Model, Roles, and Capability Uplift
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 8 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
18.1 | Template 18.1 — Role Profile Delta Table
Traditional PMO role |  | Decision-Grade PMO role |  | Capability change required
PMO Lead |  | Service Portfolio Owner |  | From process governance to service ownership: managing a catalogue of decision services, each with its own LoA, gate, and assurance commitment.
PMO Manager |  | Service Owner (per domain) |  | Accountable for one domain service end-to-end: data quality, gate operation, output defensibility. Reads QA reports as a first-class artefact.
Reporting Analyst |  | Evidence Spine Custodian |  | From building decks to maintaining a controlled, queryable evidence base. SQL/data-model literacy. Comfortable refusing to publish.
Cost Engineer |  | Cost Service Owner |  | Same craft, plus accountability for the AI-assisted forecast challenge service: knowing when to override, knowing when to escalate.
Planner / Scheduler |  | Planning Service Owner |  | Same craft, plus operating the schedule-quality QA service at LoA 1–2: deciding which flagged exceptions are real.
Risk Manager |  | Risk Service Owner |  | Same craft, plus operating QRA-quality and risk-pattern detection at LoA 2: signing off on cluster outputs before they reach the gate.
Assurance Lead |  | Assurance Partner |  | From periodic review to control-test design: building and operating a sampling regime against published outputs and the gates that produce them.
(new) |  | Data & Tooling Owner |  | Accountable for the integration layer, data foundation and AI service health. Sits inside the PMO, not in central IT. Speaks both languages.
(new) |  | AI Service Reviewer |  | Human-in-the-loop role for LoA 2–3 outputs. Domain-trained, AI-literate, with documented sign-off authority and a published refusal record.
18.2 | Template 18.2 — Role RACI (service-level)
FIELD / CONTROL |  |  | WORKING ENTRY
Activity
Service owner
Domain analyst
Data Product owner
Workflow owner
Reviewer
Approver
Assurance
18.3 | Template 18.3 — Competency Matrix (role-based)
FIELD / CONTROL |  |  | WORKING ENTRY
Role
Evidence discipline
Decision writing
Data literacy
GenAI drafting hygiene
Assurance behaviours
Confidentiality handling
Notes
18.4 | Template 18.4 — Training Pathway (by role)
FIELD / CONTROL |  |  | WORKING ENTRY
Role
Mandatory modules
Optional modules
Practice exercises
Assessment/check
Refresher cadence
18.5 | Template 18.5 — Service Runbook Outline (minimum viable)
FIELD / CONTROL |  |  | WORKING ENTRY
Purpose and decisions supported
Inputs, cut-offs, and Data Product references
Weekly routine (triage, exceptions, actions)
Monthly routine (governance pack, approvals, publication)
Gates and checklists
Escalation rules
Roles and responsibilities
Safe mode triggers and incident route
18.6 | Template 18.6 — Publish Rights Register
Output type |  | Who can draft |  | Who can review | Who can approve/publish | Restrictions | Logging requirement
18.7 | Template 18.7 — Assurance Interface Routine (calendar + tests)
FIELD / CONTROL |  |  | WORKING ENTRY
Sampling cadence
Tests (reproducibility, evidence retrieval, permissions, overrides)
Sample selection rules
Reporting route
Actions and escalation
18.8 | Template 18.8 — NC Service Catalogue and Ownership Map
FIELD / CONTROL |  |  | WORKING ENTRY
NC service
Service owner
Decision owners/forums
Key outputs
Cadence
Key gates (review/approve/publish)
Evidence Spine requirements
Notes
18A | Checklist 18A — Operating model readiness for AI-enabled services
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Service catalogue defined with named service owners
□ | Decision forums and LoA aligned to services
□ | Publication Gates and pack owners defined
□ | Prompt/template and rule change control in place
□ | Evidence and retrieval expectations operational (Chapter 12)
□ | Access controls and audience variants defined (Chapters 13 and 15)
□ | Runbooks exist for core services
□ | Role-based training pathways implemented
18B | Checklist 18B — Reviewer checklist (GenAI and automated outputs)
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Evidence references exist for key claims
□ | No unsupported causation or implied commitments
□ | Facts, interpretation, options, and limitations are separated
□ | Cut-off and version are visible
□ | Audience variant and distribution are correct
□ | Decision required and action ownership are clear
18C | Checklist 18C — Preventing the “AI bottleneck”
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Domain service owners own outputs and definitions
□ | Standard templates and runbooks reduce bespoke demand
□ | Digital & Data enables, but does not own content
□ | Approved prompt/template library exists for common tasks
□ | Capacity planning for the NC team is explicit (Chapter 13)
THE DECISION-GRADE PMO · COMPANION PACK · Ch18_Operating_Model_Roles_an

## Ch19_Failure_Modes_Ethics_and
Chapter 19 — Failure Modes, Ethics, and Risk Management
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 6 TEMPLATES · 4 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
19.1 | Template 19.1 — Output Consequence Classification
Output |  | Classification (exploratory/operational/governance-facing) |  | Audience variant |  | Approval required | Evidence Spine required | Notes
19.2 | Template 19.2 — Failure Modes Register (per service)
Failure mode |  | Cause hypothesis |  | Detection method | Preventive controls | Containment (safe mode action) | Owner | Escalation route
19.3 | Template 19.3 — Safe Mode Playbook
FIELD / CONTROL |  |  | WORKING ENTRY
Service
Safe mode trigger(s)
Immediate containment actions
Decision owner for safe mode activation
Communications approach (audience variants)
Technical rollback steps (rules/prompts/templates/models)
Validation steps before resuming
Post-incident review questions
19.4 | Template 19.4 — Incident Record and Corrective Action Plan
FIELD / CONTROL |  |  | WORKING ENTRY
Incident ID and date/time
What happened (facts)
Impacted outputs (versions/audiences)
Containment actions
Root cause hypothesis and validation plan
Corrective actions (owner, due date)
Preventive actions (owner, due date)
Closure evidence
19.5 | Template 19.5 — People Impact Assessment (for AI-enabled services)
FIELD / CONTROL |  |  | WORKING ENTRY
Service/output:
Potential people impacts (allocation, opportunity, workload, reputation):
Data used (role/skill vs individual):
Prohibited uses:
Fairness checks to apply:
Human accountability and appeal route:
Confidentiality classification and distribution controls:
19.6 | Template 19.6 — Change Control Record (AI assets)
FIELD / CONTROL |  |  | WORKING ENTRY
Change ID
Output type (rule/prompt/template/model/retrieval corpus)
Current version → proposed version
Reason for change
Impact assessment (comparability/confidentiality/decision integrity)
Tests performed and evidence
Approvals
Effective date
Rollback plan
19A | Checklist 19A — Safe GenAI use for governance outputs
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Inputs restricted to approved sources/structured fields
□ | Internal evidence references included for key claims
□ | Facts separated from hypotheses
□ | Limitations block included
□ | Reviewer sign-off recorded
□ | Output classified correctly (governance-facing vs exploratory)
19B | Checklist 19B — Agent workflow controls
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Workflow gates defined (retrieve → validate → draft → review → approve → publish)
□ | Write-back restricted (draft-only unless approved)
□ | Permissions aligned to audience variants
□ | Event logs captured for every step
□ | Safe mode triggers defined and tested
□ | Rollback route documented
19C | Checklist 19C — Incident handling (control failure)
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Log incident (facts; impacted outputs)
□ | Contain (safe mode if needed)
□ | Notify appropriate stakeholders using audience variants
□ | Identify root cause hypothesis and validate
□ | Implement corrective and preventive actions
□ | Record closure evidence and lessons learned
19D | Checklist 19D — Definition and output change control
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Change record created (rule/prompt/template/model)
□ | Impact on comparability assessed
□ | Tests performed; evidence attached
□ | Approvals recorded
□ | Effective date and rollback plan set
□ | If governance outputs are affected, publish a change notice
THE DECISION-GRADE PMO · COMPANION PACK · Ch19_Failure_Modes_Ethics_and

## Ch20_Measuring_Value_Without
Chapter 20 — Measuring Value Without Chasing Vanity Metrics
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 6 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
20.1 | Template 20.1 — Value Hypothesis Card (per service increment)
FIELD / CONTROL |  |  | WORKING ENTRY
Service/increment
Decision(s) improved
Current failure mode
Intended operating change
Measures (primary/secondary/control health)
Baseline period
Target direction (improve/reduce/increase)
Risks and unintended consequences
Owner
20.2 | Template 20.2 — Baseline Snapshot (simple, sample-based)
Measure |  | Baseline period |  | Sample size |  | Baseline value |  | Notes / data source
20.3 | Template 20.3 — NC Value Scorecard (monthly)
FIELD / CONTROL |  |  | WORKING ENTRY
Layer
Measure
Definition ref
Current
Trend
Threshold
Owner
Notes
20.4 | Template 20.4 — Measure Definition Sheet (one per measure)
FIELD / CONTROL |  |  | WORKING ENTRY
Measure name
Why it matters (decision relevance)
Calculation method (plain English)
Inputs and sources
Cut-off/cadence
Owner
Thresholds/tolerances
Failure modes / gaming risks
Change control route
20.5 | Template 20.5 — Value Review Agenda and Actions (monthly, 30–45 minutes)
FIELD / CONTROL |  |  | WORKING ENTRY
Improvements evidenced this month
Degradations or new friction points
Incidents (safe mode, permission issues, missing evidence)
Assurance sampling highlights
Changes proposed (thresholds, training, data rules)
Actions and owners
20.6 | Template 20.6 — Measure Ownership Register
Measure |  | Owner |  | Forum | Cadence | Source-of-record | Threshold | Escalation route
20A | Checklist 20A — A value measure is acceptable if…
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | It links to a decision, action, or control requirement
□ | It has a definition and an owner
□ | It is measurable from existing logs or a light sampling approach
□ | It has a baseline and a trend view
□ | It is resistant to gaming (or has a countermeasure)
20B | Checklist 20B — Avoiding vanity metrics
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Activity metrics are capped and not used as outcome proof
□ | “Time saved” claims are evidenced (observed task time reduction)
□ | Quality measures include evidence and gate compliance
□ | Control health is included (retrieval success, incidents, drift)
20C | Checklist 20C — Value review discipline
DONE | CONTROL / STANDARD | [5 empty] | EVIDENCE / NOTES
□ | Scorecard reviewed monthly with owners present
□ | Measures with definition drift are flagged and corrected
□ | Incidents and safe mode triggers are reviewed and actioned
□ | Improvement actions are tracked and closed
THE DECISION-GRADE PMO · COMPANION PACK · Ch20_Measuring_Value_Without

## Ch21_The_PMO_as_Decision_Adva
Chapter 21 — The PMO as Decision Advantage
The Decision-Grade PMO · Companion Pack
Templates from this chapter. Adapt freely. The chapter text in the book gives the rationale; this sheet gives the form. Use what fits your context.
CONTENTS: 5 TEMPLATES · 3 CHECKLISTS |  |  | PALE BLUE = WORKING ENTRY · GOLD = CONTROL / CHECKLIST · ADAPT LABELS, PRESERVE DISCIPLINE
21.1 | Template 21.1 — Decision Advantage Definition (one page)
FIELD / CONTROL |  |  | WORKING ENTRY
Decisions that matter (top 10)
Current decision failure modes (late/disputed/inconsistent)
Required cadence and cut-offs
Minimum evidence standard for decisions
What must be explicit (limitations, assumptions)
Accountability points (who signs, who decides)
What “good” looks like in 90 days
21.2 | Template 21.2 — 90-Day NC Action Plan (service-led)
Week |  | Focus |  | Outputs to publish | Gates to implement | Risks | Owners
21.3 | Template 21.3 — Decision Service Scorecard (executive view)
Service |  | Decision outcomes (cycle time / option window) |  | Service performance (timeliness / exceptions) | Control health (gate compliance / retrieval) |  | Key actions
21.4 | Template 21.4 — Decision Quality Checklist (for forums)
FIELD / CONTROL |  |  | WORKING ENTRY
Decision statement is clear and owned
Options are stated with trade-offs
Evidence is referenced (internal IDs)
Limitations and unknowns are explicit
Dependencies and constraints are declared
Actions are owned with due dates
21.5 | Template 21.5 — NC Improvement Backlog (decision-led)
FIELD / CONTROL |  |  | WORKING ENTRY
Improvement item
Decision pain addressed
Service
Effort
Risk
Priority
Owner
Due
21A | Checklist 21A — “Are we operating as an NC?”
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Services have named owners and runbooks
□ | Packs are decision-led; exceptions are prioritised
□ | Cut-offs and Publication Gates are enforced
□ | Evidence index and versioning are routine
□ | Audience variants and access controls are working
□ | Assurance sampling and retrieval readiness is routine
□ | Safe mode triggers exist and have been tested
□ | Value is measured in decision outcomes and control health
21B | Checklist 21B — Decision forum discipline
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Decisions required are stated at the start
□ | Options papers exist for material decisions
□ | Limitations and unknowns are explicit
□ | Actions are recorded and tracked
□ | Follow-through and outcome review occurs next cycle
21C | Checklist 21C — Scaling safely
DONE | CONTROL / STANDARD |  |  |  |  | EVIDENCE / NOTES
□ | Thin Slice pattern used (operability → credibility → scale)
□ | Templates and rule sets are versioned and change-controlled
□ | Monitoring and incident routines are in place
YOUR NEXT 30 DAYS
□ | You have read this book. You understand the NC operating model, the four AI capability types, the LoA ladder, and the governance principles that keep AI in the PMO trustworthy. Now comes the harder part. Here are three things you can do in the next thirty days that will matter more than any further reading: First, run an AI capability audit in your PMO. Not a technology audit a use case audit. Where is AI already being used, officially or unofficially? What decisions is it touching? Is anyone governing it? You will be surprised what you find. Second, identify one manual process in your PMO that consumes more than four hours per week and has well-defined inputs and outputs. Scope an automation pilot. Keep it small. Run it in twelve weeks. Third, have one honest conversation with your sponsor about AI governance. Not about capability or cost about accountability. When the AI is wrong, who carries it? If you cannot answer that question clearly, you are not ready to scale. The practitioners who will define the AI-enabled PMO are not waiting for a perfect framework. They are starting now, with imperfect tools, and learning faster than those who are still planning to start.
□ | Start now. The PMO of the future is built by the practitioners of today.
□ | Role-based training and reviewer capability exist
□ | Templates and checklists from this appendix are available in editable format at tsri.ai/files. The same page carries the book’s tables and figures as separate downloads, a searchable subject index, and any corrections issued after publication.
THE DECISION-GRADE PMO · COMPANION PACK · Ch21_The_PMO_as_Decision_Adva

## Prompts_All
Governed prompt library
75 prompts across seven PMO workflows
75 PROMPTS | 7 WORKFLOWS | 1 PUBLICATION GATE | Use prompts inside governed workflows. Review evidence, limitations and publication status before any governance-facing release.
# | Workflow | Prompt title | Prompt text | Notes / context
D1.1 | 1. Diagnose (current-state assessment) | Decision friction log | From the last four steering group packs and their minutes, list every item raised, the expected outcome (decision / information / escalation), what actually happened, and the time elapsed from first raised to outcome. Flag items where the outcome was “deferred for more information” or “escalated”. Do not invent rationale not present in the minutes. Output: table with columns item, raised date, expected outcome, actual outcome, elapsed days. | Designed for RAG-enabled access to pack PDFs and minutes. Without RAG, paste the relevant extracts directly.
D1.2 | 1. Diagnose (current-state assessment) | Digital PMO maturity self-assessment | Using the five-row, four-stage self-assessment grid from Chapter 1 (data & cut-offs, evidence, decision discipline, assurance, AI governance), assess [programme name] against each row. Base the assessment only on the evidence I paste below (the last three period-close packs, the latest assurance review, the risk register export). Highlight disagreements between the evidence and any self-described maturity. Output: table with stage rating per row and a one-line justification per cell citing evidence.
D1.3 | 1. Diagnose (current-state assessment) | PMO output quality audit | Review the attached steering group pack for [period]. For each section, identify (a) whether it ends in a decision, action, or is informational only; (b) whether data cut-off is stated; (c) whether evidence references are present; (d) whether any numeric claim lacks a source. Do not invent sources. Output: table with section, type, cut-off stated Y/N, evidence references Y/N, unsourced claims count.
D1.4 | 1. Diagnose (current-state assessment) | Option window map (current state) | For the decisions listed in [decision register], identify for each (a) when options existed and were cheap to exercise, (b) when the window started closing, (c) when the decision was actually made, and (d) whether the decision was made before the window closed. Use only the evidence in the register and the associated exception log. Flag decisions where the window closed before the decision was made.
D1.5 | 1. Diagnose (current-state assessment) | Escalation pattern analysis | From the last eight executive meetings’ agendas and minutes, identify items that were unplanned escalations (not on the original agenda). For each, trace back to the first internal forum where the exception was raised. Output: table with item, first raised, first escalated, elapsed days, whether the first internal forum’s minute records an owner and a decision attempt. Do not infer escalation where it is not recorded.
D1.6 | 1. Diagnose (current-state assessment) | Pack-to-decision conversion rate | Given the last four period-close packs [paste or reference], calculate: number of items presented, number resulting in a decision at first presentation, number deferred, number escalated. Express as percentages. Do not weight by item importance. Output: simple table and a one-paragraph observation highlighting any trend across the four periods.
D1.7 | 1. Diagnose (current-state assessment) | Dispute frequency audit | From the last three governance forums’ minutes, list every instance where a number presented in the pack was disputed by an attendee. For each, record: which number, by whom, the basis of challenge (if minuted), and whether the dispute was resolved in the meeting. Do not infer disputes not present in the minutes. Output: table; summary counts by source system of the disputed number.
D1.8 | 1. Diagnose (current-state assessment) | AI realism screen (where it could help) | Given the decision-friction log [D1.1], the maturity self-assessment [D1.2], and the output quality audit [D1.3], identify three decisions where an AI-enabled NC service could plausibly shorten cycle time, reduce dispute frequency, or protect option windows. For each, specify the decision, the current failure mode, the proposed change, and a test of whether it would move a measurable outcome. Do not claim improvement without a measurable outcome proposed.
D2.1 | 2. Frame (service design and scoping) | Decision set and owners | From the list of decisions surfaced in [D1.4], produce a prioritised decision set for the first-wave NC scope. For each decision include: owner (named role), forum, cadence, the three most critical inputs, and the principal consequence class (cost, schedule, safety, regulatory). Flag any decision without a single accountable owner.
D2.2 | 2. Frame (service design and scoping) | Decision service card (design) | For [decision name], design a decision-service card following Template 6.1 structure: purpose, decision supported, owner, cadence, inputs and systems of record, outputs, publication rules, LoA per step, escalation route. Use only inputs you can verify exist in [programme data landscape]. Do not propose integrations to systems that are not listed.
D2.3 | 2. Frame (service design and scoping) | NC cadence map | Design a weekly + monthly NC cadence for [programme name] that covers: weekly exception triage, monthly service calibration, and the standing governance forums (list from [governance calendar]). Show the handoff points between them. Do not introduce new forums; reorganise existing ones.
D2.4 | 2. Frame (service design and scoping) | Service-to-domain integration map | For the first-wave services from [D2.1], map each to its source-data domains (schedule, cost, risk, change, resource, other). For each intersection, state what the service needs, who owns the source, and the cut-off dependency. Flag any intersection where the source owner is not identified.
D2.5 | 2. Frame (service design and scoping) | First-wave service shortlist | From the candidate services in [D2.1], score the top five against two criteria: value (how much it improves a named decision in [decision friction log D1.1]) and controllability (how readily its data, publication rules, and Level of Autonomy can be established within one quarter). Use a 1–5 scale; include justification per score. Output: ranked table; recommended first-wave selection (max two services).
D2.6 | 2. Frame (service design and scoping) | Service value hypothesis | Write a value hypothesis for [service name] following Template 20.1: the decision to improve, the current failure mode (from [D1.1]), the intended change, how it will be measured (before/after), the expected measurable outcome. Do not propose a measure that cannot be taken from an existing data source.
D2.7 | 2. Frame (service design and scoping) | Level of Autonomy map (by step) | For [service name], break the service into its operating steps and assign an LoA per step from the five-rung ladder (LoA 0 No AI / 1 Assist / 2 Recommend / 3 Route / 4 Publish (restricted)). For each, state the evidence reference rule and the human review requirement. Do not assign LoA 3 or higher to any step whose output is published externally without review.
D2.8 | 2. Frame (service design and scoping) | Evidence-led output rules (one page) | For [service name], draft a one-page output rules document: allowed inputs (system-of-record only), required evidence references for key claims, prohibited behaviours (no invention, no causation without evidence, no hidden assumptions), standard limitations block when evidence is weak, reviewer checklist reference, routing rule for evidence gaps.
D2.9 | 2. Frame (service design and scoping) | Minimum publication standard (one page) | Draft the one-page publication standard for outputs from [service name]: cut-off discipline, version ID scheme, evidence index requirements, limitations block position, reviewer/approver authorities, confidentiality classification, audience-variant rules. Do not rely on rules not currently in force in [programme]; flag where new rules are required.
D2.10 | 2. Frame (service design and scoping) | Safe-mode triggers | Define the safe-mode triggers for [service name]: specific failure conditions (data gap, definition drift, evidence retrieval failure, LoA breach, external dispute), the threshold per trigger, the immediate action (pause / revert / relabel exploratory), who can trigger, and who must be informed. Do not propose triggers without a measurable threshold.
D3.1 | 3. Build data and evidence (foundation layer) | Decision-critical data inventory | For [service name], build the decision-critical data inventory (Template 5.1): one row per Key Data Element required by the service. Populate from the sources I paste or that are retrievable from [system landscape]. Do not populate entries you cannot verify. Flag rows where owner or source-of-record is ambiguous.
D3.2 | 3. Build data and evidence (foundation layer) | KDE definition, source, thresholds | For the KDE [name] in [service name], write the full definition (unambiguous), the system of record (named), the extraction method, the completeness and freshness thresholds, and the known exceptions. Verify consistency with any existing data dictionary. Do not write definitions that depend on unstated assumptions.
D3.3 | 3. Build data and evidence (foundation layer) | Identifier and coding standard | For [programme], audit the identifier and coding usage across [schedule tool] and [cost tool]. List identifiers present in both; identifiers present in one only; coding mismatches (same identifier with different codes). Do not reconcile differences; report them. Output: three tables.
D3.4 | 3. Build data and evidence (foundation layer) | Cut-off discipline rules | Draft the cut-off discipline for period-close outputs from [service name]: cut-off day and time, extraction sequence, reconciliation window, late-data rules, documentation requirements. Base on current operating constraints; flag conflicts with existing cut-offs in [other services].
D3.5 | 3. Build data and evidence (foundation layer) | Data product card | For [data product] following Template 13.2: product purpose, consumers, source KDEs, cut-off, quality rules, release cadence, publication rules, access classification. Do not include consumers or sources not verifiable from the service and data landscape documentation.
D3.6 | 3. Build data and evidence (foundation layer) | Integration and transformation register | For [data product], document each transformation from source to published form: source system, field, transformation rule, target field, tested against samples Y/N, change-control reference. Flag transformations without tested sample reconciliation.
D3.7 | 3. Build data and evidence (foundation layer) | Evidence Spine index | For the outputs from [service name], build the evidence index for the current period: for each numeric claim in the output, the source system, extraction timestamp, version ID, reviewer, approver, and location of supporting calculation. Do not claim evidence retrieval that has not been demonstrated in sample tests.
D3.8 | 3. Build data and evidence (foundation layer) | Evidence lineage validation | For [output / pack], take five numeric claims at random and trace each end-to-end: stated value in output, published calculation, underlying data extract, system of record. For each claim, mark traceable / partially traceable / not traceable. Do not fill in gaps; report them.
D3.9 | 3. Build data and evidence (foundation layer) | Audit trail design | For [service name], design the audit trail: what is logged (inputs, versions, prompts, outputs, reviewers, approvers, publication events), retention period, access controls, restoration procedure, and alignment to [regulatory requirement if applicable]. Flag any log requirement without a named owner.
D3.10 | 3. Build data and evidence (foundation layer) | Data quality threshold setting | For the KDEs in [D3.1], propose completeness and freshness thresholds that would currently be met 95% of the time, based on the rolling 12-period history I supply. Do not propose thresholds above current demonstrated performance; flag KDEs whose historical performance is unmeasured.
D3.11 | 3. Build data and evidence (foundation layer) | Drift detection scan (data drift and model drift) | For the named NC service, identify the inputs subject to data drift (changes in source data shape or distribution) and the components subject to model drift (changes in model behaviour). For each, define the test the weekly cadence will run and the threshold that triggers revalidation. Do not assume that completeness checks detect distribution change.
D4.1 | 4. Triage and analyse (the domain services) | Schedule float consumption anomaly scan | From the latest schedule export [P6 file], compare float consumption this period against (a) the planned rate in the rebaselined schedule and (b) the trailing four-period average. Flag activities where consumption exceeds the planned rate by more than 1.4× for two consecutive periods. Do not recommend schedule action; report the signal.
D4.2 | 4. Triage and analyse (the domain services) | Critical path compression risk | From [schedule file], identify activities on the critical or near-critical path (within 5 working days of total float) where progress in the last period was below plan. Rank by potential consequence if the slip is confirmed next period. Do not propose mitigations; output a prioritised watchlist for the triage forum.
D4.3 | 4. Triage and analyse (the domain services) | What-if schedule scenario | Given the schedule [file] and the proposed scenario [e.g. 6-week delay to foundations], report the forward impact on milestones M1–M5 and the critical path position at each milestone. State explicitly what the model does not account for (resource levelling, commercial constraints, weather). Label: exploratory.
D4.4 | 4. Triage and analyse (the domain services) | Cost trend anomaly detection | From the last 12 periods of cost actuals [cost sheet], flag work packages where the trend breaks its own pattern (step change, acceleration, or deceleration) beyond the bounds observed in the preceding 12 periods. Rank by absolute exposure. Do not explain causes; the service is to detect, not to diagnose.
D4.5 | 4. Triage and analyse (the domain services) | EAC variance driver analysis | Given the latest EAC [file] and the prior quarter’s EAC, identify the work packages contributing most to the period-on-period EAC shift. For each, report the contributing KDE movements. Do not propose corrective action or characterise the drivers as positive or negative beyond their arithmetic sign.
D4.6 | 4. Triage and analyse (the domain services) | Forecast reconciliation | Reconcile this period’s forecast against last period’s forecast plus actuals plus change. Identify reconciling items, unreconciled movements, and any line where the explanation is missing. Do not fabricate explanations; list unreconciled items explicitly.
D4.7 | 4. Triage and analyse (the domain services) | Risk exposure prioritisation | From [risk register], rank risks by current exposure (probability × impact), filtered to top quartile. For each, identify whether the assessment is unchanged, increased, or decreased since last period; the owner; and whether the next review is scheduled. Do not alter ratings; report the register as maintained.
D4.8 | 4. Triage and analyse (the domain services) | QRA output summary | From the QRA output [file], summarise the P50, P80, P95 positions for cost and schedule; the top five drivers of variance; the change from prior QRA. State model assumptions explicitly. Label: assurance-supported, not a forecast.
D4.9 | 4. Triage and analyse (the domain services) | Change request triage | From the open change log, categorise each change by (a) type (scope, time, cost, quality), (b) governance level required, (c) status against the agreed turnaround, (d) supporting evidence completeness. Flag changes where the governance route is unclear or supporting evidence is incomplete.
D4.10 | 4. Triage and analyse (the domain services) | Contract exposure map | From [contract register / variation log], summarise the top contract exposures by supplier, the nature of the exposure (cost, delay, dispute), and the current position. Do not characterise dispute merits; report status only.
D4.11 | 4. Triage and analyse (the domain services) | Resource demand forecast | From the resource-loaded schedule and the resource register, forecast the 12-period resource demand curve by discipline. Flag the three largest gaps between demand and current secured supply. Do not propose recruitment responses; output the gap map.
D4.12 | 4. Triage and analyse (the domain services) | Capability gap analysis | For the first-wave NC services [from D2.5], identify capability gaps in the current PMO team: named role types required, current gap (FTE), skill gap description. Base on the role-profile templates and the current team roster; do not name individuals.
D4.13 | 4. Triage and analyse (the domain services) | Exception routing | For the exceptions raised this week [list], route each to its correct forum and owner using the cadence map [D2.3] and the decision-service cards. For each, state target resolution date, evidence required, and whether the owning forum is within its cadence window. Do not downgrade the exception severity to fit the cadence.
D4.14 | 4. Triage and analyse (the domain services) | Leading indicator synthesis | From [domain signals: float consumption, cost trend, change velocity, risk drift], identify concurrent signals across domains that may indicate a single emerging issue. Name the candidate issue; cite the supporting signals; state the counter-evidence. Do not claim causal connection without counter-evidence addressed.
D4.15 | 4. Triage and analyse (the domain services) | Portfolio signal aggregation | Across [portfolio of programmes], aggregate the period leading indicators into a single portfolio view: ranked by aggregate signal strength, highlighting programmes with concurrent signals in two or more domains. Do not collapse signals to a single score; preserve the domains.
D5.1 | 5. Publish governance-grade outputs | Steering group pack structure | Draft the running order for the next [forum] pack using the decision spine (facts → exceptions → options → decisions). For each section identify the input service, the owner, the required evidence. Do not include content without an identified service and owner.
D5.2 | 5. Publish governance-grade outputs | Decision spine conversion | Convert the attached draft pack into decision spine format: lead with the decisions required at the forum, support each with a one-page options paper, link options to their evidence references. Remove sections that inform without leading to a decision unless they are explicitly labelled as context.
D5.3 | 5. Publish governance-grade outputs | Option paper template application | For [decision name], draft an option paper: problem statement (one paragraph), options (minimum two, maximum four), option-by-option criteria comparison (cost, schedule, risk, evidence strength), recommendation with justification, limitations. Do not produce a single-option recommendation unless the paper explicitly states why no other option is viable.
D5.4 | 5. Publish governance-grade outputs | Audience variant generation | From [pack master version], produce the redacted audience variant for [attendee group] following the audience-variant rules (Template 4.4). Identify exactly which sections are redacted, replaced, or summarised, and why. Do not remove material the audience is entitled to receive; do not include material the audience is not entitled to.
D5.5 | 5. Publish governance-grade outputs | Limitations block for AI-assisted output | For [output section] produced with AI assistance at LoA [x], draft the limitations block: what the AI did, what evidence it used, where its output was reviewed and by whom, what it did not attempt (caveats), what the reader should treat as firm and what as provisional.
D5.6 | 5. Publish governance-grade outputs | Evidence index for a pack | For the forthcoming [forum] pack, build the evidence index: for each numeric claim, a reference ID linking to the source extract; for each narrative claim, a reference to the supporting evidence; for each recommendation, a reference to the supporting option paper.
D5.7 | 5. Publish governance-grade outputs | Publication gate checklist application | Apply Template 4.3 (Publication Gate Checklist) to [output]: walk the checklist, state the status of each field with reference to evidence, identify fields that cannot yet be signed off. Do not mark a field complete without evidence reference.
D5.8 | 5. Publish governance-grade outputs | RAG narrative explainer | For the RAG position [e.g. “Amber” on [workstream]], write the one-paragraph narrative that accompanies it: what the RAG reflects, the three KDEs driving the rating, the change since last period, what action is expected. Do not write narrative that softens the RAG rating.
D5.9 | 5. Publish governance-grade outputs | Action register with owners | From the forum minutes [paste or retrieve], extract every action: description, accountable owner, target date, success criterion, review cadence. Flag actions without a named individual owner or a measurable success criterion. Do not re-describe actions in your own words; preserve the minute text.
D5.10 | 5. Publish governance-grade outputs | Minute-to-action conversion | From the draft minutes [paste], identify the decisions, the actions, and the information points. For decisions, confirm decision owner, resolution text, evidence referenced. For actions, produce D5.9 output. Flag any implied decision that is not explicit in the minutes.
D5.11 | 5. Publish governance-grade outputs | Four-region mapping for an NC service | For the named NC service, map each step onto the four-region consequence and autonomy plane (Region 1 to 4). State the LoA for each step, the consequence of failure for each step, and the resulting region. Identify any step that would shift region if the consequence of failure rose. Do not aggregate steps with different LoAs into a single region; preserve the per-step granularity.
D6.1 | 6. Assure and audit (control health) | Publication Gate compliance check | For the last four period-close packs, apply Template 4.3 retrospectively. Score each on gate compliance; identify the fields most commonly missed; rank the findings by consequence. Do not reclassify findings to reduce the count.
D6.2 | 6. Assure and audit (control health) | Evidence retrieval test | Select five numeric claims at random from [output]. For each, attempt to retrieve the full evidence chain (source, extract, version, reviewer, approver). Measure retrieval time and success. Report the results with times per claim. Do not stop the test at the first failure; complete the sample.
D6.3 | 6. Assure and audit (control health) | AI output auditability review | For AI-assisted output [name], review for auditability: are the prompts stored with version IDs; are the data inputs referenced; are the LoAs stated; are the reviewers named; are the limitations blocks present. List gaps without proposing fixes.
D6.4 | 6. Assure and audit (control health) | LoA conformance check | For the services [D2.7], sample three outputs each and check whether the LoA stated matches the LoA operated. In particular, check whether outputs labelled LoA 1 show evidence of human-level interpretation, and outputs labelled LoA 3 show evidence of human review. Do not rationalise discrepancies; report them.
D6.5 | 6. Assure and audit (control health) | Safe-mode activation review | From the last period’s safe-mode activation log [from D2.10], analyse each activation: trigger, duration, impact on service output, recovery path, root cause. Identify any recurring trigger. Do not recommend removal of a safe-mode trigger without a root-cause resolution.
D6.6 | 6. Assure and audit (control health) | Definition drift scan | For the KDEs in [D3.1], compare the current definition in use against the version committed six months ago. Flag any definition change without a corresponding change-control record. Do not retrospectively approve drift; report as a finding.
D6.7 | 6. Assure and audit (control health) | Assurance evidence pack assembly | For the forthcoming Independent Assurance Review, assemble the evidence pack: the four standard reports with their evidence indices, the period’s safe-mode log, the Publication Gate findings, the data-quality metrics. Do not include evidence not supporting a claim in scope; do not omit evidence for claims in scope.
D6.8 | 6. Assure and audit (control health) | Root cause analysis of a control failure | Given [control failure description and evidence], produce the root-cause analysis following [standard framework]: the sequence of events, the contributing factors (data, definition, LoA, review, approval), the corrective action, the preventive action. Do not assign blame to an individual; analyse the control.
D6.9 | 6. Assure and audit (control health) | Source-claim verification | For [output / pack / chapter section], identify every factual source claim, standard reference, regulatory reference, benchmark, statistic, and external authority cited or implied. For each claim, state: the exact claim, source named or required, whether the claim is evidenced, whether the source is current, whether wording should be softened, and the recommended action. Do not invent sources. Where a claim cannot be verified from the material supplied, mark it as [SOURCE NEEDED] or recommend removal.
D6.10 | 6. Assure and audit (control health) | CAE chain test for a published output | For one published output, walk the chain from claim through argument to evidence. For each material claim in the output, identify the operating logic (argument) that produced it and the evidence that supports it. Flag any claim whose argument cannot be reconstructed or whose evidence is not retrievable. Do not accept narrative confidence as a substitute for evidence.
D6.11 | 6. Assure and audit (control health) | Operating threshold review for classifier-based services | For each classifier-based service in the NC, retrieve the current operating threshold and the date of the last review. State the false positive rate, the false negative rate, and the consequence class of each output. Flag any service whose threshold has not been reviewed within the defined cadence or after a change in consequence class. Do not optimise threshold against reviewer workload alone.
D6.12 | 6. Assure and audit (control health) | Service transfer re-validation check | For any NC service that has been transferred from one programme or portfolio context to another in the last twelve months, retrieve the re-validation evidence: data quality thresholds, LoA ceiling, Publication Gate criteria, sampling discipline, shadow-mode period. Flag any transfer where re-validation evidence cannot be retrieved. Treat absence of re-validation evidence as a finding.
D7.1 | 7. Measure and sustain (value realisation) | Value hypothesis card for a new service | For [new service], complete the Value Hypothesis Card (Template 20.1): the decision to improve, the current failure mode, the intended change, the measurement approach before and after, the expected measurable outcome. Do not commit to a measurable outcome that cannot be calculated from existing sources.
D7.2 | 7. Measure and sustain (value realisation) | Baseline snapshot | Capture the baseline for [service]: cycle times, option window protection rate, escalation rate, assurance rework hours, forecast variance, period-close cycle, Publication Gate compliance. Use the prior four cycles. Do not smooth outliers; preserve them with annotation.
D7.3 | 7. Measure and sustain (value realisation) | NC value scorecard | Build the NC Value Scorecard (Template 20.3) for [service] at quarter-close: decision outcomes layer, service performance layer, control health layer. For each measure, state the definition, the source, the baseline, the current value, the delta, and the note on attribution.
D7.4 | 7. Measure and sustain (value realisation) | Monthly value review agenda | Draft the agenda for the monthly value review of [service]: measures at a glance (5 min), exceptions (15 min), control health (5 min), actions (5 min). Populate with the current-period data. Limit items to 30 minutes total; remove items that cannot be discussed within the cadence.
D7.5 | 7. Measure and sustain (value realisation) | Forecast accuracy tracking | Track forecast accuracy for [cost / schedule] over the last eight periods: forecast at period-start vs actual at period-end, absolute variance, trend. Do not blend domains; report each separately.
D7.6 | 7. Measure and sustain (value realisation) | Benefits realisation note (conservative) | Write the quarterly benefits realisation note for [service]: directly-evidenced benefits with attribution share, risk-adjusted benefits with methodology disclosed, unrealised hypotheses from [D7.1], adjustments to the business case. Do not re-claim benefits whose attribution logic has not held up.
D7.7 | 7. Measure and sustain (value realisation) | Capability uplift plan | From [D4.12 capability gap], plan the capability uplift for the next two quarters: roles, target capability level, development path per role (training, shadow, supervised practice, independent), review points. Do not commit to a development path that exceeds the funded development budget.
D7.8 | 7. Measure and sustain (value realisation) | Roadmap status update | For the Digital PMO roadmap [file], produce the quarterly status update: services delivered vs plan, services in progress with RAG, services delayed with reason, next two quarters’ priorities. Include the value realised per delivered service from [D7.3]. Do not re-plan silently; flag every rephasing.

## Glossary
Glossary
Quick reference for the working language used throughout the book and companion pack
Definitions are deliberately concise. Use the book for the rationale, boundaries and worked context behind each term.
Term | Working definition
CPI | Cost Performance Index = EV / AC. CPI > 1 = under budget; CPI < 1 = over budget.
SPI | Schedule Performance Index = EV / PV. SPI > 1 = ahead of plan; SPI < 1 = behind.
TCPI | To-Complete Performance Index = (BAC − EV) / (BAC − AC). Cost efficiency required for remaining work to finish at budget.
EAC | Estimate at Completion. Forecast of total project cost. Often EAC = BAC / CPI.
BAC | Budget at Completion. Total planned budget for a project or phase.
EV / PV / AC | Earned Value / Planned Value / Actual Cost. The three earned-value primitives.
QRA | Quantitative Risk Analysis. Probabilistic modelling of cost/schedule outcomes (Monte Carlo).
P50, P80 | Percentile forecasts. P50 = median; P80 = conservative (80% confidence).
KDE | Key Data Element. A data field formally identified as required for one or more decision services, with named ownership, definition, refresh cadence, and quality criteria.
KPI | Key Performance Indicator. In the NC model, decision-outcome focused, not activity-focused.
LoA | Level of Autonomy. The autonomy posture for an AI-assisted output: 0 None, 1 Assist, 2 Recommend, 3 Route, 4 Publish-restricted.
NC | Nerve Centre. The operating model this book describes.
PMO | Project Management Office. In the NC model, a decision and intelligence service, not a compliance service.
DAS | Decision-Augmented System. AI-augmented operating arrangement in which AI strengthens human decision-making within governed services. Distinguished from autonomous agents and from raw chat-style AI use.
LFE | Learning From Experience. Two related uses: (i) a Nerve Centre discipline of capturing what worked, what did not, and the evidence trails behind both; (ii) a cross-programme reference base of Learning From Experience databases and risk materialisation records.
Publication Gate | The release control through which any AI-augmented governance-facing output must pass before publication. See Master Template M2.
Evidence Spine | The structured backbone of inputs, sources, model versions, and approvals that supports a Publication-Gate-compliant output. See Master Template M3.
Thin Slice | An end-to-end first service increment, deliberately narrow in scope, that exercises the full NC operating model in real conditions.
Three Numbers | The measurement trio used to make the value case: decision cycle time (issue raised to decision made and communicated), forecast accuracy (against a measured baseline, by domain), and escalation reduction (unplanned escalations to board and steering level). Worked cases instantiate the trio with programme-specific figures rather than borrowed ranges.
FM-X1 to FM-X6 | The Master Failure Mode Taxonomy: GenAI hallucination (X1), agents publishing without gates (X2), confidentiality breach (X3), autonomy creep (X4), definition drift (X5), evidence gaps masked by narrative (X6).
RACI | Responsible, Accountable, Consulted, Informed. Used in Master Template M4.
ISO 42001 | International AI Management System standard. Where regulated AI is in scope, accountable ownership sits with a separate AI governance function rather than the PMO.
Sovereign cloud | Cloud infrastructure constrained by jurisdiction and classification rules. Used for AI deployment in regulated environments where data sovereignty is a regulatory requirement.
HAZOP | Hazard and Operability study. Structured safety review used in process and nuclear engineering.
ONR | Office for Nuclear Regulation (UK). The regulator for the Stellar running case.
SNI | Sensitive Nuclear Information. Classification applied to nuclear-site data under the UK Nuclear Industries Security Regulations 2003.
AI Quality Plan | The controlled artefact stating what good looks like for an AI-assisted service and how a decline would be detected. Covers product quality and quality in use. One per service, versioned, owned by the service owner. See Master Template M5.
Learning loop | The five-stage cycle that turns a predictive signal into governed learning: signal, human review, intervention, outcome, learning. Each stage has an owner and a record. Signal quality and intervention effectiveness are evaluated separately.
Data-readiness gate | The decision point at which a data-readiness review resolves to proceed, proceed with named constraints, or do not proceed, for a stated scope and use. A review that produces only a description has not reached a gate.
Automation bias | The tendency of a reviewer to accept an output because a system produced it. Shows in the data as a falling amendment rate, which is indistinguishable from genuine improvement without a blind review sample.
Drift | Change over time in the input data (data drift) or in the relationship the model learned (concept drift), such that a validated model no longer performs as validated. Detected by monitoring, not by inspection.
Holdout / out-of-time validation | Two tests a predictive model should pass before operational approval. A holdout test withholds whole projects, not random records. An out-of-time test trains up to a cut-off and tests on the period after it.
Provenance record | The facts captured at publication that let an AI-assisted output be explained afterwards: model and version, prompt or workflow version where material, sources retrieved, named reviewer, approval timestamp, substantive amendments, retention.
THE DECISION-GRADE PMO · COMPANION PACK · Glossary

## Change_Log
Change log
A controlled record of companion-pack releases
Each release records what changed, who made the change and any implications for readers using an earlier pack.
Date | Summary of changes | Author | Notes
April 2026 | First release. All Appendix D prompts (69 across 7 workflows) and Appendix E templates (Chapters 1–15, 17–21). | Steven A Thomson
2026-07-27 | Reconciled to the published book: added the six Appendix D prompts missing from the first release (D3.11, D5.11, D6.9, D6.10, D6.11, D6.12) so the pack carries all 75; added the Chapter 16 sheet (The Predictive PMO in Operation); corrected the prompt counts on the Cover and Index; removed a duplicate Change log entry from the Index. | Larry (for Steve) | Pack now matches the book exactly: 75 prompts, Chapters 1–21.
2026-07-31 | Reconciled to the book. Added Master Template M5, the AI Quality Plan (product quality and quality in use), which the book registers in Appendix E. Corrected three glossary definitions that contradicted the book: LFE is Learning From Experience (not Lessons Learned and Evidence); SNI is Sensitive Nuclear Information (not Site Nuclear Information); and Three Numbers is the measurement trio of decision cycle time, forecast accuracy and escalation reduction (the previous ROI-framed definition was superseded). Added seven glossary terms introduced in the book: AI Quality Plan, learning loop, data-readiness gate, automation bias, drift, holdout and out-of-time validation, provenance record. | Steven A Thomson
2026-08-07 | Reconciled to the book. Added Template 13.8, Submission Contract Specification, which the book cites as the output of the new Chapter 13 section The Submission Contract. Added the governed-submission line to Checklist 13C, since the book makes the governed submission the default integration pattern rather than API-first. | Steven A Thomson
2026-08-08 | Presentation rebuild. Every template and checklist is now a structured, fillable grid — field and working-entry columns, evidence columns on the checklists, and a colour legend — replacing the fixed-width text blocks carried since the first release. Content is unchanged from the previous pack: 5 master templates, all templates and checklists for Chapters 1–21, 75 prompts. | Steven A Thomson | Nothing added or removed. A reader on the previous pack loses no content by moving to this one; the templates simply became usable.
2026-08-14 | Cover correction. The cover carried a publisher imprint line, on the artwork and again as a heading above it. The imprint was withdrawn in August 2026 and this book is published under no imprint: the copyright page names no publisher and the ebook declares none. Both are removed here and the cover artwork is replaced with the artwork already corrected for the book itself. | Steven A Thomson | Cover only. No template, checklist, prompt or glossary entry is added, removed or renumbered: 5 master templates, 219 templates and checklists for Chapters 1–21, and 75 prompts, all identical to the previous pack.
2026-08-14 | Numbering reconciled to the book. Four numbered artefacts did not resolve to the instrument the book names at that number. Template 18.1 is now the Role Profile Delta Table, taken from the table the book prints in Chapter 18. Template 4.4 is now the book-wide Audience Variant Rules, the fixed identity Appendix E gives it; the three chapter-specific versions at 11.10, 12.8 and 15.5 are unchanged. Template 14.7 is now the Control Improvement Backlog and Checklist 14B is now the Audit Retrieval Checklist, each restored by swapping with the artefact that had displaced it. The two displaced Chapter 4 and Chapter 18 templates keep their content and move to 4.8 and 18.8. Prompt D5.4 pointed at Template 4.3 and now points at Template 4.4. If you are working from an earlier pack, five numbers have moved. | Steven A Thomson | Chapters 4, 14 and 18 only. Nothing the book does not cite by number is renumbered. 216 numbered templates and checklists for Chapters 1–21 (214 in the previous pack, plus the two authored here), 5 master templates, 75 prompts in the same order, 28 sheets.
2026-08-15 | Prompt D2.7 conformed to the book. It told you to assign a Level of Autonomy from a four-level framework; the book uses a five-rung ladder, LoA 0 No AI / 1 Assist / 2 Recommend / 3 Route / 4 Publish (restricted), and the prompt's own next sentence refers to LoA 3, which the four-level list does not contain. The prompt text is now the book's, word for word. Template 20.5 is renamed to the name the book gives it, Value Review Agenda and Actions, keeping the monthly cadence and the 30-45 minute duration. Nothing is renumbered and no other prompt is changed. | Steven A Thomson | Two cells. 221 numbered artefacts, 75 prompts in the same order, 28 sheets, all unchanged from the previous pack. Nine further prompt-wording differences against the book are measured and NOT changed here, so they stay visible.
2026-08-16 | Version numbering withdrawn. This is now simply the Companion Pack. The cover carried a version number for the pack and another for the manuscript it was built against, and both went stale whenever either moved — the cover was still naming an earlier manuscript five revisions after the book had moved on. A number that nothing keeps current is worse than no number, because it reads as though somebody is checking. This change log is now kept by date, and the pack you have is the pack that is published: download it again and you have the current one. | Steven A Thomson | Presentation only. No template, checklist, prompt or glossary entry is added, removed, renumbered or reworded: 221 numbered artefacts, 75 prompts in the same order, 28 sheets, all unchanged.
2026-08-27 | Companion address corrected. This sheet sent readers to a domain that was never registered. The book printed the same address in four places until July 2026, when a registration check found it did not exist and all four were repointed; this pack was one day old at the time and was missed, so it has carried a dead address ever since. It now reads tsri.ai/files, which is what the book prints. The sentence around it is corrected too: the page does not separately hold the Decision Service Card, Publication Gate and Evidence Index. It holds this workbook, and those are in it. | Quire (for Steve) | One cell of content, plus this row. Nothing is added, removed, renumbered or reworded anywhere else. Counted in this file after the change: 28 sheets, 75 prompts, 150 numbered templates and 66 numbered checklists. A reader on the previous pack loses no content by moving to this one and gains an address that resolves.
THE DECISION-GRADE PMO · COMPANION PACK · Change_Log